## Pilot Plan
CJAP Robot — Pilot Execution Plan (3 weeks, 2-person)
<100-doc pilot . Member 1 leads implementation (Claude Code) . Member 2 supports (prep, curation, eval, docs)
OBJECTIVE
Prove, on a curated subset of fewer than 100 documents, that the hybrid retrieval + Sonnet composition pipeline produces high-fidelity, in-voice CJAP responses with acceptable latency and an improving cost-per-query, before scaling to the full 1,000+ document corpus.
TEAM & WORKING MODEL
Member 1 - implementation lead | Owns the code path via Claude Code: repo, chunking, embeddings, sparse arm, fusion, routing, composer, payload slimming, caching, evals.
Member 2 - support | Corpus prep & normalisation QA, pilot doc-set curation, exemplars, eval-set authoring, output verification, metrics recording, document deliverables (Cowork).
Working pattern | Two parallel tracks with hand-offs: Member 2 prepares/curates and verifies what Member 1 builds; Member 1 consumes Member 2's frozen inputs. Respect the Depends order.
SCOPE SPLIT (full corpus vs pilot subset)
Taxonomy = full corpus | The topic map, clustering, centroids and independence check are built on the FULL ~1,000-doc corpus, so topic structure, orphaned content and empty topics are seen accurately - a 100-doc slice would distort them (a topic may look orphaned at 100 but be well-populated at 1,000).
Pilot run/eval = <100 | The pipeline is RUN and EVALUATED on the curated <100 subset, tagged against the full taxonomy. Small = fast to iterate and hand-checkable for grounding/fabrication. Composer latency & cost are per-query, independent of corpus size.
ARCHITECTURE AT A GLANCE
Offline build | Normalised UTF-8 corpus; heading-aware chunks + doc store keyed by doc_id; dense embeddings (bge-large @1024d, local); BM25 sparse index + curated keyword/entity dictionary; topic centroids; date index; Voice Card.
Runtime - code | Query embed -> centroid scoring -> theme/topic routing; hybrid fusion (dense + sparse, RRF) -> top-k chunks; deterministic register + disclaimer selection. No LLM in this path.
Retrieval principle | Topics BIAS retrieval (a soft prior + register/disclaimer driver); PASSAGES decide (passage-level ranking); the sparse arm rescues exact identifiers. Topics never hard-gate retrieval - a routing error must not hide the right passage.
Runtime - Sonnet | Composition only: slim payload (top-k chunks + lean directives + cached Voice Card prefix) -> ENVELOPE. Streamed.
Embedding model | bge-base-en-v1.5 local @768d — RATIFIED after a 4-candidate bake-off (recall vs cost/latency/on-device fit). bge-large-en-v1.5 @1024d archived with a documented rollback; MiniLM and hosted text-embedding-3 were the other candidates. Same model for docs, queries and centroids; resident at service start, zero per-call cost, data stays on-prem.
Biggest cost lever | Payload slimming (chunks not whole docs) + prompt-caching the static prefix - not the embedding model or the router.
LATENCY / COST GUARDRAILS (from architecture review)
Measure p95 & TTFT | Track p95 and time-to-first-token, not just medians - the worst-case paths (fallback double-call, cold start, cache miss, API variance) inflate p95, not the median you look at first.
Output side too | Output tokens drive cost/latency as much as input: cap max_tokens, give the Voice Card length discipline, and stream prose (don't wrap the visible answer in JSON).
Treat as gates | Expand-on-demand fire-rate (target < ~10%) and cache-hit rate are release gates; default top-k starts low and rises only when recall@k demands it.
Retrieval cutoff | Dynamic relevance cutoff (keep chunks with score >= tau*top_score) bounded by min_k/max_k - adapts chunk count to relevance, not a fixed top-k.
Config & voice | All knobs in one config.py (tau, min_k/max_k, max_tokens, lambda, thresholds). Voice front-end: stream -> sentence-chunk -> TTS; optional in-voice Haiku filler; NO raw reasoning-trace narration.
PHASE SUMMARY (3 weeks)
Week | Theme & focus
Week 1 | Foundation + hybrid retrieval (two weeks condensed) - stabilise + unified config.py, normalise corpus, freeze the <100 pilot subset, chunk + embed, sparse arm + keyword dictionary, taxonomy on the FULL corpus, fusion + code routing (dynamic relevance cutoff), latency baseline, decisions memo.
Week 2 | Composition, payload slimming & guardrails - Sonnet composer + ENVELOPE, slim payload, prefix caching, date index, threshold + theme-as-control-signal disclaimer, expand-on-demand, voice/TTS front-end.
Week 3 | Evaluate, tune & decide - eval set, quality + latency/cost evals, payload sweep to the knee, fusion/threshold tuning, pilot report + Go/No-Go, ADRs.
AFTER THE PILOT
Corpus maintenance | From Sept 2026 the corpus grows and is corrected through the Project Plan v2 runbook (Data Flow + Corpus Expansion sheets). Tracked here as CM-1…CM-6 on the Weekly Tasks sheet.

## Weekly Tasks
Weekly Task Tracker - CJAP Robot Pilot (<100 docs) . 3-week, 2-person playbook (Member 1 + Member 2)
Member 1 = implementation (Claude Code). Member 2 = support: prep, curation, verification, docs (Cowork). Subtasks tagged [Member 1]/[Member 2]. Update Status as you go.
ID | Week | Task | Subtasks (with owner) | Lead | Claude Code / Cowork prompt (paste-ready) | Result / acceptance | Status | Blocked on | Evidence (path / commit / artifact)
W1.1 | Week 1 | Stabilise codebase + unified config.py | - Audit branches; consolidate to one clean branch; resolve conflicts [Member 1] - Tag baseline 'pilot-baseline'; set up pilot working dir [Member 1] - Create unified config.py: tau, min_k/max_k, max_tokens, fusion lambda, thresholds, model IDs, timeouts [Member 1] - Confirm end-to-end run; document env/setup steps [Member 2] | Member 1 | Open the repo (Supervaise-Reachy-Mini-Project). Audit branches, consolidate to one clean working branch, resolve conflicts, tag 'pilot-baseline', and confirm an end-to-end run. Create a SINGLE config.py (or a YAML it loads) holding every tunable knob - relevance threshold tau, min_k/max_k, max_tokens, fusion weight lambda, out-of-scope/topic thresholds, model IDs, timeouts - so the W3.3 sweep varies config, not code. Output a short changelog + env/setup steps. | Single clean branch; baseline tagged (pilot-baseline = CODE/CONFIG baseline, pre-W1.7 rebuild & pre-W1.8 build); config.py centralises all knobs (46). Regression run passed; live e2e DEFERRED to W1.11 arch-baseline. | DONE — ~78+ knobs centralized; env-overridable |  | config.py¦CHANGELOG.md
W1.2 | Week 1 | Normalise & prep the corpus | - Write normalisation script: mojibake->UTF-8, quotes/dashes [Member 1] - Safely parse JSON-list fields; casefold/strip keywords [Member 1] - Re-save utf-8-sig, ensure_ascii=False [Member 1] - Run on all curated CSVs; QA rows changed; spot-check 10 docs [Member 2] - Log unparseable fields for follow-up [Member 2] | Member 1 | Write/run a normalisation script for the curated CSVs (e.g. cjp_columns_curated.csv): fix cp1252 mojibake (0x97 em-dash, 0x91-0x94 smart quotes, 0x9d) to UTF-8, normalise curly quotes/dashes to ASCII, safely parse JSON-list fields (Keyword/s, primary_topics, sub_topics, signature_phrases, entities), casefold/strip keyword tokens, re-save as utf-8-sig with ensure_ascii=False, and report rows changed + unparseable fields. | Clean UTF-8 corpus; mojibake=0; QA report; issues logged. | DONE — corpus normalization (defined in this plan; audit UNKNOWN because deliverable is off-repo) |  | data/csv/*_curated_normalized.xlsx (audit counted 1089/8887 built from them)
W1.3 | Week 1 | Freeze the pilot/eval subset (v4 ALLOWLIST, <100) | - Re-freeze as v4: balanced 95 docs (19/theme), <100 cap restored; supersedes v3/v2/v1 (all retained) [Member 2] - v4 is an EVAL-TIME ALLOWLIST of doc_ids (consumed at W1.5/W3) - it does NOT drive chunking [Member 2] - Re-derive forced lists from full corpus: fix CA060 (indigents != indigenous) + SD035 (not climate); expand under-inclusive AI-governance set; keep all forced docs [Member 2] - Relabel: "balanced for per-theme eval power" (NOT "representative"); strata = coarse curated-theme (ADR-0011 letter), to be re-tagged at W1.7; biography GC### = ID-convention artifact [Member 2] - Output v4 frozen list + coverage table + forced-inclusions (with keyword evidence) + selection notes [Member 2] | Member 2 | Re-freeze the pilot subset as v4: a balanced 95-doc (19/theme) EVAL-TIME ALLOWLIST of doc_ids - NOT the chunking input (W1.4 chunks the FULL corpus). Restore the <100 cap (v3 broke nothing but v2 did); retain all forced docs but RE-DERIVE the AI-governance + orphaned-topic lists from the full normalised corpus (operationalise: Keyword/s field, casefold at tally, strip person-name tokens, orphaned <=2 docs). Fix the CA060 (indigents, not "indigenous peoples") and SD035 (FLP Scholars/COVID, not "climate") mislabels with keyword evidence; expand the under-inclusive AI set (CE018/CA095/CE019/...). Drop the "representative" claim - label it "balanced for per-theme eval power" and state the corpus is ~55% theme A. Relabel strata as coarse curated-theme (ADR-0011 ID letter, NOT the W1.7 taxonomy, which does not exist yet); reword the biography note as an ID-convention artifact. Read corpus from the confirmed data/csv/*_curated_normalized.xlsx. Do NOT modify v1/v2/v3. If re-derived forced docs push a theme past 19, FLAG for a PM call - do not silently drop a forced doc. Output: pilot_subset_frozen_v4.csv, coverage_table_v4.csv, forced_inclusions_v4.csv (with keyword evidence), selection_notes_v4.txt. | Frozen v4 ALLOWLIST (<100, expect 95 balanced) + coverage table handed to Member 1. Forced lists re-derived (CA060/SD035 corrected, AI set expanded); "representative" claim removed; theme/biography framing fixed; v1/v2/v3 retained. | DONE — 95 docs; v4 frozen 2026-06-27; v1-v3 retained |  | reports/pilot-eval subset/pilot_subset_frozen_v4.csv
W1.4 | Week 1 | Corpus prep + FULL-corpus chunking + doc store (pinned) | - Regenerate the corpus/ markdown tree FROM the four data/csv/*_curated_normalized.xlsx (repoint generate_corpus_files.py off the stale 80-doc CSVs) [Member 1] - PIN the corpus: track xlsx in git + corpus_snapshot.json (per-file sha256 + per-doc row hash) + verify_pin.py that fails on drift [Member 1] - Heading-aware chunking (~200-400 tokens, small overlap) over the FULL ~1,089-doc corpus; all knobs from config.py [Member 1] - Build doc store (chunk_id -> doc_id, metadata + anecdotes) + chunk index; built ONCE, stable across subset re-freezes [Member 1] - Verify: all 95 pilot-allowlist docs resolve to chunks; boundaries + anecdotes verified [Member 1] | Member 1 | Chunk the FULL ~1,089-doc corpus (architecture decision: subset is an eval-time allowlist, NOT the chunk input). FIRST regenerate the corpus/ markdown tree from the confirmed data/csv/*_curated_normalized.xlsx - the existing tree is built by generate_corpus_files.py from the STALE 80-doc tracked CSVs (no books), so 89/95 pilot docs are currently missing; repoint that script to the xlsx and regenerate all ~1,089 docs (doc_id = padded Article Code; entities stays a JSON object). THEN pin the corpus so "frozen" is verifiable: track the four xlsx in git (or commit CSV exports) and write corpus_snapshot.json with per-file sha256 + per-doc row_sha256 (canonical 15-field serialization) + a producer/date header; add scripts/verify_pin.py that recomputes both and exits nonzero on drift. THEN heading-aware chunk (~200-400 tokens, small overlap, knobs from config.py) the full corpus, retaining anecdotes and respecting section boundaries; build the doc store + chunk index ONCE. Verify: full corpus chunked; all 95 pilot-allowlist doc_ids resolve to chunks (the missing-89 problem is gone); boundary + anecdote spot-checks on a sample including several of the 95; verify_pin passes. Report corpus count (+ the 1,059-vs-1,089 discrepancy with the real number), chunk stats, and the 95-doc resolution check. | Full corpus regenerated from xlsx + chunked; doc store + chunk index built (once, stable); anecdotes retained; boundaries verified; ALL 95 allowlist docs resolve; corpus PINNED (snapshot + verify_pin PASSES). Subset is an allowlist applied at W1.5/W3, not here. | DONE — heading-aware chunks; snapshot-pinned |  | corpus/index/chunks.jsonl (8887/1089)¦scripts/verify_pin.py PASS
W1.5 | Week 1 | Embed the pilot subset (runtime index) | - Load chosen model: bge-large-en-v1.5 @1024d (local, strong, resident) - swappable via config.py [Member 1] - Load model ONCE at service start (resident) - never per-request, to avoid cold-start spikes [Member 1] - Embed the <100 subset chunks; numpy float32 matrix + persist [Member 1] - Same model/dim for queries, centroids & full-corpus taxonomy (W1.7) [Member 1] - Apply search_query/search_document input types (bge supports them) [Member 1] | Member 1 | Embed the <100 pilot-subset chunks with bge-large-en-v1.5 @1024d (LOCAL, resident; model id lives in config.py so it stays swappable - MiniLM and OpenAI text-embedding-3 are the alternatives benchmarked in W3.4). Local-strong is chosen over MiniLM (quality) and over hosted GPT/OpenAI (keeps the query off the network hot path, no per-call cost, corpus/queries never leave our infra). Load the model ONCE at service start and keep it resident to avoid cold-start spikes. Store vectors in an in-memory numpy float32 matrix indexed by chunk_id, persisted to .npy + json. Use the SAME model/dim for queries, centroids, and the full-corpus taxonomy (W1.7). Apply bge search_query/search_document input types. | Pilot-subset index embedded with bge-large (local, resident), persisted and queryable; model id config-driven. | DONE |  | data/index/pilot_dense.npy + pilot_dense_meta.json (95/827; bge-large; cuda_fp32)
W1.6 | Week 1 | Build the sparse arm (BM25) | - BM25 index over full chunk text [Member 1] - Load curated keywords+entities as atomic-phrase dictionary [Member 1] - Keep multi-word keywords as single terms (no whitespace split) [Member 1] - Expose sparse_score(query) -> ranked chunk_ids [Member 1] - KEEP BM25 regardless of dense model: no embedding matches exact identifiers (complementary, not redundant) [Member 1] | Member 1 | Build a BM25 index over full chunk text. Load the normalised curated Keyword/s + entities as an atomic-phrase boost dictionary - treat each multi-word keyword as a single term (do NOT whitespace-tokenise; 91% are multi-word). Expose sparse_score(query) returning ranked chunk_ids. Keep the sparse arm regardless of which dense embedding is used (MiniLM/bge/OpenAI) - exact-identifier matching is complementary to semantic recall, not redundant. | BM25 + keyword dictionary returns ranked chunks. | DONE |  | data/index/pilot_sparse.pkl¦sparse_phrase_dict.json¦pilot_sparse_meta.json
W1.7 | Week 1 | Regenerate topic map FROM SCRATCH on FULL corpus (new centroid model) + tag subset | - Rebuild centroids from scratch under the new dimensional model: centroid = mean(label + description + signature_phrases + exemplar chunks) [Both] - Embed the full ~1,000-doc corpus offline (bge-large, local) [Member 1] - Re-run independence check (cosine > 0.85 merge) + coverage/orphaned-content analysis; do NOT carry over or incrementally expand the old 35-topic map [Both] - Tag the frozen <100 pilot subset against the regenerated centroids (1-3 topics, primary+secondary) [Member 1] - All topic-model params read from config.py (TOPIC_MERGE_COSINE, MAX_TOPIC_TAGS, CENTROID_SOURCE_FIELDS) [Member 1] | Both | Regenerate the topic map FROM SCRATCH on the FULL ~1,000-doc corpus under the new dimensional/centroid model - do NOT start from or expand the existing 35-topic map (it is stale: its own health check flags independence violations above the 0.85 bar). Each topic centroid = mean(label + description + signature_phrases + exemplar chunks). Embed the full corpus offline with bge-large-en-v1.5 (the same local model as W1.5). Re-run the independence check (merge pairs with cosine > TOPIC_MERGE_COSINE) and a coverage analysis (flag orphaned content with no matching topic). Then tag the frozen <100 pilot subset against the regenerated centroids (primary + secondary, up to MAX_TOPIC_TAGS). Read every topic-model knob from config.py. Report: topic count, merged pairs, coverage gaps, and the subset tagging summary. | Topic map REGENERATED from scratch (not incrementally expanded); independence + coverage re-analysed; orphaned content flagged; pilot subset tagged; fully config-driven. | DONE |  | data/index/topic_centroids.npy + topic_centroids_meta.json (n_topics=34; merge 0.95; floor 0.68 locked)
W1.8 | Week 1 | BUILD the new retrieval architecture - Haiku-out, centroid + RRF hybrid, soft prior | - Remove the Haiku router entirely from the serial path; delete the pre-retrieval LLM round-trip [Member 1] - Deterministic code router: query embed -> centroid scoring -> softmax + out-of-scope gate -> theme/topic select as SOFT PRIOR, not a hard gate [Member 1] - Hybrid fusion: bge-large dense + BM25 sparse via RRF -> ranked passages [Member 1] - Soft-prior scoring: score = passage_sim + lambda*topic_affinity; global fallback when prior weak [Member 1] - Dynamic cutoff: keep chunks where score >= tau*top_score, bounded by min_k/max_k [Member 1] - Deterministic selection: register/theme cues, Theme-A disclaimer template, date resolution [Member 1] - Every knob from config.py (no new literals); deprecate/remove vestigial ROUTER_MODEL_ID [Member 1] | Member 1 | BUILD the new retrieval architecture (this is a BUILD, not a tune - the architecture is design-only today and the live path is still Haiku->Sonnet). Branch off the current pilot branch. Read all knobs from config.py; introduce NO new literals; do NOT tune weights/thresholds (that is W3.4 - use config defaults). Preconditions (confirm they exist, else stop and report): dense index (W1.5), BM25 sparse (W1.6), regenerated centroids (W1.7). 1) REMOVE HAIKU: delete the pre-retrieval Haiku call; after this ZERO LLM round-trips before composition - prove via per-stage timing; mark ROUTER_MODEL_ID deprecated. 2) CODE ROUTER (soft prior): query embed (resident bge-large, no cold start) -> centroid cosine -> softmax -> relevance vector; OUT_OF_SCOPE_THRESHOLD decides in/out; theme selection BIASES, never gates; weak prior falls through to global retrieval. 3) HYBRID RRF: dense + BM25 fused by RRF (RRF_K); apply score = passage_sim + LAMBDA*topic_affinity with global fallback (guard the orphaned-content failure mode). 4) DYNAMIC CUTOFF: keep score >= TAU*top_score, bounded MIN_K/MAX_K. 5) DETERMINISTIC SELECTION: register/theme cues, deterministic Theme-A disclaimer, date resolution; assemble slim top-k payload (chunks, not whole docs). 6) e2e on the <100 subset at config defaults (needs ANTHROPIC_API_KEY); paste command + grounded sample + per-stage timing showing no pre-composition LLM call. Flag inconsistencies; do not silently fix outside scope. | Haiku fully removed (per-stage log shows ZERO LLM round-trips before composition). Centroid scoring + RRF passage ranking live; soft prior + global fallback + dynamic cutoff all config-driven. Deterministic theme/date selection. Runs e2e on the <100 subset at config defaults. NO tuning here (that is W3.4). | DONE — llm_calls_before_composition==0 verified in every baseline |  | app/retrieval.py¦app/service.py¦commit fc66b9e ancestors
W1.9 | Week 1 | Latency logging + baseline | - Per-stage timing (input gate->router->retrieval->composer) [Member 1] - Capture time-to-first-token (TTFT) separately from total [Member 1] - JSON-lines logs + p50/p95 summary script (report p95, not just median) [Member 1] - Warm the model/service before measuring (steady-state, not cold) [Member 1] - Run baseline on current pipeline over draft queries [Member 1] - Record baseline latency/TTFT/cost/quality to Pilot Metrics [Member 2] | Both | Add per-stage timing (ASR if present -> input gate -> router -> retrieval -> composer) emitting JSON-lines logs, plus a script summarising p50/p95 per stage. Capture time-to-first-token separately from total latency and report p95 (not just median). Warm the model/service before the baseline run so you measure steady-state, not cold-start. Run the frozen pilot set through the current pipeline and write baseline latency (e2e + per-stage + TTFT), cost/query and quality to baseline.json. | Per-stage + TTFT logging live; warmed baseline (p50/p95) recorded. | DONE — 10-query constructed stand-in set (pre-freeze) |  | baseline.json¦baseline.jsonl¦commit 340b843
W1.10 | Week 1 | Lock decisions memo | - Record embedding model, store, hybrid architecture [Member 2] - Record routing + theme-as-control-signal decisions [Member 2] - Set latency/quality/cost targets in Pilot Metrics [Member 2] - Circulate for sign-off [Member 2] | Member 2 | Draft a one-page Week-1 Decisions memo: embedding model (DEFAULT bge-large-en-v1.5 local @1024d; MiniLM and OpenAI text-embedding-3 are benchmarked alternatives, final call from the W3.4 bake-off), in-memory numpy retrieval, hybrid dense+sparse(BM25)+keyword dictionary, centroid topic dimensions, deterministic code routing, theme-as-control-signal, and latency/quality/cost targets. One decision per row with rationale + owner. | Decisions memo signed off; targets entered. | PARTIAL — artifact exists; sign-off status UNKNOWN; memo never committed | Member 2 | W1.10_Decisions_Memo.md + .docx (LOCAL-ONLY untracked)
W1.11 | Week 1 | arch-baseline checkpoint - first new-arch e2e + latency/cost anchor | - Run the first full pilot e2e on the <100 subset through the NEW architecture [Member 1] - Capture per-stage latency p50/p95 + TTFT (+ TTFA if voice path wired) [Member 1] - Verify Haiku absent from the path; record cached vs uncached compose cost if caching present [Member 1] - Tag arch-baseline (annotated) as the OFFICIAL W3.3 sweep anchor - NOT pilot-baseline [Member 1] - Enter the numbers into metrics sheet / decisions memo [Member 2] | Member 1 | Run the first real end-to-end of the new architecture on the <100 pilot subset (needs ANTHROPIC_API_KEY). Capture per-stage latency p50/p95 and TTFT (and TTFA if the voice front-end is wired). Verify empirically that Haiku is absent from the path (no LLM round-trip before composition). If prompt caching is in place, record cached vs uncached compose cost. Then create an annotated tag arch-baseline and document it as the OFFICIAL latency/cost comparison anchor for the W3.3 sweep - pilot-baseline must NOT be used (it is the old Haiku-in-path, un-slimmed-payload baseline). Hand the numbers to Member 2 for the metrics sheet / decisions memo. | New-arch e2e returns a grounded answer; per-stage + TTFT baseline recorded; Haiku-absence verified; arch-baseline tag created and designated the W3.3 comparison anchor. | DONE — 40/40 native; $0.665 run cost recorded |  | tag arch-baseline (caa3c8c)¦arch_baseline.json
W2.1 | Week 2 | Sonnet composer + ENVELOPE (guardrails) | - Wire retrieved chunks + plan into Sonnet call [Member 1] - Stream the prose; carry ENVELOPE metadata as a trailing block - do NOT wrap the visible answer in JSON [Member 1] - Set max_tokens cap; Voice Card length discipline (e.g. 3-5 paragraphs unless asked to expand) [Member 1] - Timeouts + bounded retries w/ backoff; graceful degradation message [Member 1] - Keep Sonnet (not Haiku) [Member 1] - Smoke-test 5 queries per theme [Member 2] | Member 1 | Wire retrieved chunks + routing plan into the Sonnet composition call. STREAM the user-facing prose directly and carry the ENVELOPE metadata {doc_ids_cited, register_used, anecdotes_deployed, signature_phrases_used} as a separate trailing block or light second pass - do NOT wrap the visible answer inside JSON that must fully arrive before rendering (that kills streaming). Set a max_tokens cap and give the Voice Card explicit length discipline (e.g. 3-5 paragraphs unless asked to expand), since output tokens drive cost/latency too. Add request timeouts + bounded retries with backoff and a graceful 'let me get back to you' degradation path. Keep Sonnet, not Haiku. | Streamed prose + trailing metadata; max_tokens + timeouts/retries in place. | DONE — COMPOSER_MAX_TOKENS=640; 0 truncation; graceful degradation proven live |  | commits 4a115e5+3ef2e05¦w2_1_baseline.json
W2.2 | Week 2 | Payload slimming | - Pass top-k chunks (not whole docs) [Member 1] - Role-filtered enrichment per doc_id [Member 1] - Directives = theme + register + Theme-A compliance only [Member 1] - signature_phrases optional palette; exclude stances/decision-framework/audience/register_markers [Member 1] - Make top-k + chunk budget config params [Member 1] | Member 1 | Slim the composer payload: top-k matched chunks only (not whole docs) + role-filtered enrichment per doc_id. Directives = theme + register + Theme-A compliance; pass signature_phrases as an OPTIONAL palette ('use when natural'); EXCLUDE stances/decision_framework_signals/target_audience/register_markers (keep them diagnostic). Make top-k and chunk budget config params. | Payload = chunks + lean directives; params configurable. | DONE — -48.8% input tokens measured on 9q probe; default ships behavior-preserving |  | commit 0aedbd7¦w2_2_payload_report.json
W2.3 | Week 2 | Prompt-cache the static prefix | - Static prefix first (Voice Card + persona + Theme-A disclaimer) [Member 1] - Variable content (chunks, query, date) last [Member 1] - Confirm prefix clears the cache minimum-size threshold (or it won't cache) [Member 1] - Enable Anthropic prompt caching; log cost CACHED vs UNCACHED separately [Member 1] | Member 1 | Restructure the composer prompt so all static content (Voice Card, persona instructions, Theme-A disclaimer) is one prefix placed FIRST and variable content (chunks, query, date) LAST. Confirm the static prefix clears the cache minimum-size threshold (or it won't cache at all). Enable Anthropic prompt caching and log cost-per-query CACHED vs UNCACHED separately - pilot traffic is sporadic so the cache TTL may expire between queries; project production cost from the cached number but report the pilot's actual (likely uncached) number honestly. (Do this first in Week 2 - pure win, no quality risk.) | Prefix cached (min-size confirmed); cached vs uncached cost logged. | DONE — no leak; stable cache_read; pilot cost = UNCACHED caveat |  | commit 2bb64aa¦w2_3_cache_report.json
W2.4 | Week 2 | Build the date index | - Add dates to .md front matter [Member 2] - Build markdown date index table [Member 1] - Deterministic temporal-query resolver -> doc_ids [Member 1] - Remove date-stuffing from payload; pass current date only [Member 1] | Both | Move dates to .md front matter, build a markdown date index, and a deterministic script resolving temporal queries ('last month','late 90s') to doc_ids. Remove date-stuffing from the Sonnet payload; pass only the current date for phrasing. | Temporal queries resolve via index; payload de-bloated. | DONE (dark: DATE_INDEX_ENABLED=false) — verified no-regression + idempotent |  | eval/results/w2_4_date_index_selfcheck.json
W2.5 | Week 2 | Threshold + theme-as-control-signal | - Out-of-scope threshold + graceful fallback message [Member 1] - Theme score selects register block + Theme-A disclaimer template [Member 1] - Sonnet is told the theme (does not infer) [Member 1] - Confirm disclaimer wording with counsel / counsel [Member 2] - Verify disclaimer present on all Theme-A responses [Member 2] | Both | Implement the out-of-scope threshold + graceful fallback. Make the deterministic theme score SELECT the register instruction block and the Theme-A legal disclaimer template (education/opinion, never advice) - Sonnet is told the theme, not inferring it. Ensure every Theme-A response carries the disclaimer. | Out-of-scope handled; Theme-A disclaimer deterministic + approved. | DONE — confirm-only; no new W2.5 code; tuning deferred W3.4 |  | app/retrieval.py soft-prior + global fallback (W1.8 code)
W2.6 | Week 2 | Expand-on-demand fallback (gated) | - Detect weak retrieval (low fusion score / missing-context) [Member 1] - Fetch fuller doc for the doc_id; recompose - cap to a SINGLE retry [Member 1] - Log fire-rate; treat as a release GATE (fix upstream if > ~10%) [Member 1] | Member 1 | Add a second-pass fallback: if retrieved chunks are insufficient (low fusion score or composer signals missing context), fetch the fuller document for the doc_id and recompose - capped to a SINGLE retry (the second call ingests a larger document and doubles the most expensive stage). Log the fire-rate and treat it as a release GATE, not just a metric: if it exceeds ~10%, the fix is upstream (better chunking or a slightly wider initial top-k), not more fallbacks. | Single-retry fallback; fire-rate logged and gated (< ~10%). | DONE (dark: EXPAND_ON_DEMAND_ENABLED=false) — hard-cap=1 proven; fire-rate 0/40 @floor=1 |  | eval/results/w2_6_expand_report.json
W2.7 | Week 2 | Voice/TTS front-end (stream -> TTS) | - Approach 3 backbone: stream Sonnet output; chunk at SENTENCE/clause boundaries; feed TTS incrementally [Member 1] - Confirm TTS consumes incrementally (else the streaming gain is lost) [Member 1] - Optional: in-voice Haiku filler if a pre-generation pause remains (Approach 1) [Member 1] - Simpler alt first: tighter max_tokens to cut generation time [Member 1] - DECISION: NO raw reasoning-trace narration (Approach 2) - off-voice + leakage risk [Member 1] - Measure time-to-first-audio (TTFA) [Member 2] | Member 1 | Build the voice front-end after the composer. BACKBONE (Approach 3): stream Sonnet's output and feed TTS incrementally, chunked at sentence/clause boundaries (never mid-token); confirm the TTS engine accepts incremental input or the streaming gain is lost. Keep the prose unwrapped (no JSON). ENHANCEMENT (Approach 1, optional): only if a pre-first-token pause remains, play a short IN-VOICE Haiku-composed filler while Sonnet works - the simpler first move is a tighter max_tokens. DECISION: do NOT narrate raw reasoning traces (Approach 2) - they are off-persona and leak deliberation. Measure time-to-first-audio. | Streaming TTS with sentence-boundary chunking; TTFA measured; no raw-trace narration. | PARTIAL — replay TTFA 2.5s p50 real (39/39 overlap); LIVE TTFA + Linux TTS unverified; Member 2 voice sign-off pending | robot | w2_7_ttfa_v2_report.json; design/w2_7_reachy_seam.md (d24fb0f)
W2.8 | Week 2 | Adaptive retrieval: top-k -> top-p (softmax-temp) | - Replace flat top-k; softmax-temp @ temp 0.06 over fused RRF score [Member 1] - First attempt (top-p over flat RRF) was DEGENERATE (kept ~753/827); temp version adopted - MIN_K=4 floor / ceiling 12 | Member 1 | (executed) softmax-temperature concentration over fused score in config.py | Median 9 chunks; -28% input tokens; 0 grounding losses. Commits TOPP-1 5750b6e, TOPP-2 65ce85c. W3.2 must validate MIN_K=4 floor isn't too thin. | DONE — flat-RRF top-p degenerate (~753/827 kept); flagged not fixed |  | commit 5750b6e¦reports/pilot-eval subset/w2_topp_report.json
W2.9 | Week 2 | Tag arch-baseline-v2 (going-forward comparator) | - Tag v2 after retrieval + composer changes [Member 1] - v1 (arch-baseline) is IMMUTABLE and NOT composer-comparable to v2 - All future tuning deltas measured v2-vs-v2 | Member 1 | (executed) git tag arch-baseline-v2 | Tag 704c8a6. v2 measured: TTFT p50 1.53s; TTFA 2.5s p50 / 3.7s p95; $0.0155/q cached ($0.62 / 40-run); 8.6 chunks->composer; 0/40 LLM calls before composition; 40/40 in-scope (OOS gate UNCALIBRATED, recorded as-is). | DONE — 40/40 native; answers persisted; chunks_sent mean 8.57 |  | commit 704c8a6¦tag arch-baseline-v2¦arch_baseline_v2.json
W3.1 | Week 3 | Build/extend the eval set | - Extend 49-row smoke test to a fixed pilot eval set [Member 2] - Cover grounding, AI-governance, out-of-scope, temporal, Theme-A [Member 2] - Add expected doc_ids/labels per item [Member 2] - Version-control eval_set.jsonl [Member 1] | Both | Extend the 49-row smoke test into a fixed pilot eval set covering grounding-fidelity Q&A, the AI-governance retrieval case, out-of-scope queries, temporal queries, and Theme-A compliance. Add expected doc_ids/labels and version-control as eval_set.jsonl. | Versioned eval set covering all case types. | DONE — Member 2 delivered v4-corrected gold set, 40/40 labeled (audit UNKNOWN: work arrived off-repo; canonical gold now committed) |  | eval/results/gold_reference_set.csv (fc66b9e); CJP_TaskA_RAG_Eval_Metrics_w2_1_v4gold.xlsx
W3.2 | Week 3 | Run the quality eval | - Run eval set through new pipeline [Member 1] - Score grounding fidelity; fabricated citations =0 [Member 1] - Check register_used vs expected; disclaimer present [Member 1] - Review diffs; categorise misses (retrieval vs composition) [Member 2] | Both | Run the eval set through the new pipeline. Score grounding fidelity, count fabricated citations (target 0), check register_used vs expected, and verify Theme-A disclaimer presence. Output a scored report + per-question diffs. | Quality scores vs target; fabrications=0; misses categorised. | DONE — CANONICAL: recall@1/5 = 0.735/0.971 (N=34, v4 gold, $0 regrade); fabrication 0/40; empty-cited 0; MIN_K=4 KEEP (recall-backed) |  | eval/results/w3_2_REGRADE_v3_v4gold.json (e18e1d1)
W3.3 | Week 3 | Latency/cost + payload sweep | - Sweep relevance threshold tau (+ min_k/max_k), chunk budget AND output max_tokens [Member 1] - Record fidelity, p50/p95, TTFT/TTFA, cost/query (input vs output), chunks/query [Member 1] - Start strict (high tau / low max_k); relax only when recall@k demands [Member 1] - Identify the knee; record config (tau, min_k/max_k, max_tokens) to Pilot Metrics [Member 2] | Member 1 | Run a payload sweep varying the relevance threshold tau (with min_k/max_k bounds), the chunk budget, AND the output max_tokens (output tokens drive cost/latency as much as input). For each, record grounding fidelity, latency p50/p95, time-to-first-token/audio, cost/query split input vs output, and the avg chunks admitted per query. Start strict (higher tau, lower max_k) and relax only when recall@k demands it. Identify the knee where cost/latency fall steeply while quality stays flat; recommend a config (tau, min_k/max_k, max_tokens). | Sweep over tau/min_k/max_k/chunk/output; knee config recommended. | DEFERRED → DEPLOY-1 — GO issued with 2 AMBER KPIs; tau/payload sweep folds into deploy tuning (refreshed 2026-07-27) | DEPLOY-1 | prompt doc: CJP_Composer_Sweep_W3_3.docx
W3.4 | Week 3 | Tune fusion + thresholds + soft prior | - Tune dense/sparse RRF weight on eval set [Member 1] - Tune topic-bias lambda + the weak-prior fallback threshold [Member 1] - Tune out-of-scope + topic thresholds [Member 1] - Measure routing accuracy (predicted theme/topic vs gold) [Member 1] - Measure retrieval recall@k (gold passage in top-k) [Member 1] - Confirm soft-prior beats a hard gate; re-run affected cases [Member 2] - Embedding bake-off: MiniLM vs bge-large vs OpenAI text-embedding-3 on recall@k + grounding (same pilot set) [Member 1] | Member 1 | Tune the hybrid fusion weight (dense vs sparse), the topic-bias lambda and the weak-prior fallback threshold, and the out-of-scope + topic thresholds against the eval set to maximise grounding fidelity without latency regressions. Report two diagnostics: routing accuracy (predicted theme/topic vs the gold doc's topic) and retrieval recall@k (was the gold passage in top-k). Confirm the soft-prior design holds recall@k high even when routing is imperfect - i.e. it beats a hard topic gate. Re-run affected cases and report before/after. Also run an EMBEDDING BAKE-OFF: re-embed the pilot set with MiniLM, bge-large, and OpenAI text-embedding-3, and compare recall@k and grounding fidelity on the same eval; recommend the dense model on evidence (default stays bge-large unless a gap justifies hosted, weighed against its latency/cost/data-governance cost). | Tuned weights/lambda/thresholds; routing accuracy + recall@k reported; soft-prior validated vs hard gate. Embedding bake-off recommends the dense model on evidence. Default ratified = bge-large-en-v1.5; MiniLM/OpenAI as candidates; add CM4 RAM-fit + on-device per-query latency as explicit pass/fail. | DEFERRED → DEPLOY-1 — embedder portion CLOSED via W3.14 bake-off (Sponsor ratified bge-base); fusion/lambda tuning folds into deploy tuning (refreshed 2026-07-27) | DEPLOY-1 | w3_2_REGRADE_v3_v4gold.json §B
W3.5 | Week 3 | Pilot report + Go/No-Go | - Results vs each criterion (quality/latency/cost/compliance) [Member 2] - Findings + risks [Member 2] - Go/No-Go recommendation for full-corpus scaling [Member 2] - Build Word doc (navy/gold palette) [Member 2] | Member 2 | Synthesise the eval and latency/cost results into a pilot report: results vs each success criterion (quality, latency, cost, compliance), findings, risks, and a Go/No-Go recommendation for scaling to the full 1,000+ corpus. Build as a Word doc in the navy/gold judicial palette. | Pilot report delivered; Go/No-Go decision documented. | DONE — FINAL_r2 delivered: GO recommendation, 7 GREEN / 2 AMBER KPIs (refreshed 2026-07-27) |  | CJP_Pilot_Report_W3_5_FINAL_r2.docx; CJP_Readiness_Verdict_Brief_r2.docx
W3.7 | Week 3 | Calibrate OUT_OF_SCOPE_THRESHOLD (query-time gate) | - Build a labeled in-scope / out-of-scope query set [Member 2] - Find the separation threshold on bge query->centroid cosine [Member 1] - Set OUT_OF_SCOPE_THRESHOLD in config; re-verify weather/restaurant queries are DECLINED [Member 1] | Both | Calibrate the query-time out-of-scope gate. Current OUT_OF_SCOPE_THRESHOLD=0.15 on bge's compressed cosine range = 'never refuse' -> the robot ANSWERS off-domain questions (weather, restaurants) in CJAP's voice. Build a labeled in/out set, pick the threshold, confirm off-domain -> graceful decline. | Off-domain queries declined; C.Scope + G.OOS-decline hold on real off-domain input. | DONE — OOS-close landed in combined verification; tagged arch-baseline-v4.1 (refreshed 2026-07-27) |  | tag arch-baseline-v4.1 (d806f45); w3_7_oos_calibration
W3.8 | Week 3 | Instrumentation: 3 measurement tables (retrieval/cost/compose) |  | Member 1 | (executed) Instrument 3 measurement tables (retrieval / cost / composer): add scripts/eval_instrumentation.py reading run telemetry; emit per-stage p50/p95 JSON tables; commit tables as evidence. Self-check: tables regenerate byte-stable from the same telemetry. |  | DONE — Table 2 populated (embed 535ms=86%, router 0.19ms exonerated); Tables 1/3 stubbed+self-tested, auto-populate wired. ALL UNCOMMITTED |  | latency_retrieval_$0.json; scripts/eval_instrumentation.py (LOCAL-ONLY)
W3.9 | Week 3 | arch-baseline-v3 re-baseline + v2-vs-v3 split-axis validation |  | Member 1 | (executed) Re-baseline: git tag arch-baseline-v3 after instrumentation; run v2-vs-v3 split-axis validation (retrieval must be byte-identical; only composition axis may move). STOP if retrieval diffs. Evidence: provenance JSON + diff report. |  | DONE — v3 tagged (fe75a3a); retrieval byte-identical to v2; fabrication 0/40 canonical native. NOTE: HEAD now v3+OOS+6 commits — tag v3.1 after W3.7 close |  | w3_2_PARTIAL_BC_v3_c1637cd.json; arch_baseline_v3_provenance.json
W3.10 | Week 3 | $0 evidence work: telemetry harvest + composition A/B (OOS commit gate) |  | Member 1 | (executed) $0 evidence work: harvest composer cost/TTFT from existing telemetry (no new API spend); run composition A/B on archived answers (OOS cases incl.). Evidence: compose_telemetry_harvest.json + A/B result JSON. |  | DONE — composer cost/TTFT recovered (arch-baseline-v2, directive-OFF: $0.028/q, TTFT 1.53s); A/B gate passed (0 in-scope degradation) |  | compose_telemetry_harvest.json; w3_compose_eval_0.json (LOCAL-ONLY)
W3.11 | Week 3 | Project health assessment (stage-gate review) |  | Member 3 + Claude Code | (Cowork) Run a 9-section project health assessment: audit every task row vs its evidence path; reconcile task_status.csv vs workbook; list discrepancies explicitly — do NOT silently fix statuses. Output: project_health_assessment.md + discrepancy table. |  | DONE — 9-section audit + task reconciliation; 3 discrepancies flagged (tag drift, router misattribution, evidence local-only) |  | project_health_assessment.md; task_status.csv
W3.12 | Week 3+ | Voice demo wrapper (OpenAI STT+TTS) + manual smoke test |  | Member 1 + Member 3 | Build a Streamlit voice demo wrapper: mic capture → STT (STT_BACKEND) → pipeline → streamed TTS playback; log each turn (transcript, route, TTFA) to voice_demo_log.csv. Manual smoke test with screenshot evidence. Do not modify pipeline code — wrapper only. |  | IN PROGRESS — wrapper built + demoed live (speech→transcribe→v4 retrieve+compose→TTS). Findings: (1) 2s inter-chunk TTS gap → prefetch fix tasked; (2) Baron Travel MISS live = orphan pattern, forensics tasked; (3) persona falsely claimed "not in my record" — decline-language fix proposed; (4) STT lang=tagalog quirk logged. DEMO-ONLY topology (cloud STT/TTS ≠ robot) |  | streamlit_voice_demo.py; voice_demo_log.csv; screenshot evidence
W3.13 | Debt | Evidence durability — commit + push the full evidence chain |  | Member 1 | (executed) Evidence durability: commit + push every LOCAL-ONLY evidence artifact flagged in the health assessment as grouped, labeled commits; verify tree clean afterwards. Evidence: commit range + reconciliation note. |  | DONE — 5 grouped commits pushed (3eef805..d86e976); tree clean; evidence chain durable on origin. Follow-up incident: gold CSV restore destroyed Member 2 v4 edits (numstat!=content lesson); repaired 47158f7; reconciled from her authoritative copy (690a508+6412ab0). Content-aware diffs now MANDATORY for frozen files |  | commits d86e976, 47158f7, 6412ab0; gold_incident_reconciliation.md
W3.14 | Debt | Embedder decision + v4 transition (bge-base ratified) |  | Sponsor | (executed) Prepare embedder bake-off summary for Sponsor: 4 candidates (bge-base / bge-large / MiniLM / OpenAI te-3) scored on recall@k vs cost/latency on the frozen gold set; recommendation memo; ratification recorded as ADR. Human gate: Sponsor signs before any promotion. |  | DONE — Sponsor RATIFIED C (bge-base-en-v1.5) after 4-candidate bake-off (rounds 2+3, $0). Transition executed: arch-baseline-v4 tagged (553483c); recall 0.618/0.882/0.941(@chunks-sent)/0.971; retrieval 127ms p50 (was 621); bge-large archived w/ documented rollback. Topology: on-device kept open by C |  | bakeoff_FINAL_for_dok.md (2ca0255); arch_baseline_v4_retrieval.json; tag arch-baseline-v4
NEXT STEPS — verification closure (unlocks the pilot report)
N-1 | Debt | Combined verification run: OOS close + cost/latency tables + directive-ON pass |  | Member 1 | (executed) Combined verification run (~15 composes, <$0.50): close OOS false-decline gap, populate cost/latency tables on current tags, persist all outputs. Acceptance: OOS probes pass; tables committed; tag the result (became arch-baseline-v4.1). |  | DONE — combined verification run landed; basis of arch-baseline-v4.1 (refreshed 2026-07-27) |  | tag arch-baseline-v4.1 (d806f45)
N-2 | Debt | Live TTFA measurement (the last open KPI) |  | Member 1 | (executed) Measure LIVE TTFA end-to-end (mic → first audio) across >=10 turns; break down per stage (STT / route / compose / TTS) to attribute the dominant term. Evidence: TTFA report JSON with per-stage split. Do not tune anything in this task — measure only. |  | DONE — live TTFA measured; ~4s diagnosed STT-dominant (Whisper RT 1.5–2.5s). Fix path: faster-whisper local via STT_BACKEND switch (recommended, not yet implemented; pre-answers robot MC#8) (refreshed 2026-07-27) |  | w2_7_ttfa_v2_report.json (replay-only)
N-3 | Debt | A/B corpus generation for the two blind assessors |  | Member 1 → assessors | Generate the A/B corpus for the two blind assessors (~$1.20): pair current-pipeline answers with archived directive-OFF answers per eval query; randomize A/B order per row; blind the source column; export CSV with blank winner column. Do NOT pre-fill judgments. |  | READY — ~$1.20. Pairs with archived directive-OFF answers; unblocks the end-to-end A/B Runs on v4, directive-ON — the shipping config | credits | w3_compose_eval_ab_for_sheena.csv (winner col blank)
N-4 | Debt | Gold label confirms + expanded OOS probes (Member 2) |  | Member 2 | (Cowork, prep only — labeling is Member 2, $0) Assemble the labeling packet: extract gold_confidence=low rows + expanded OOS probe candidates into one sheet with instructions and blank label columns. Do not label anything; human task. |  | READY — pure labeling, $0. Hardens OOS beyond n=2 and firms the eval floor | Member 2 | gold_reference_set.csv gold_confidence=low rows
N-5 | Debt | Credit-floor alert + billing ping monitor |  | Member 3 | Add a credit-floor alert + billing ping: config threshold (CREDIT_FLOOR_USD); check remaining credits before batch runs; refuse batch start below floor with a clear message; daily ping log. Self-check: simulate low-credit and confirm refusal path. No pipeline changes. |  | OPEN — remaining scope only: credit-floor alert + billing ping. The wake-word half of this row was superseded by the WW module and has been removed. |  | assessment §7
WAKE WORD — creation & integration (reusable module for future projects on this pipeline)
WW-1 | Module | Wake-word matcher build + offline self-test | - Token-level, boundary-safe matcher over STT transcript [Member 1] - Variant expansion from canonical phrase (single- + multi-token forms) - Committed self-test: ACCEPT set (canonical, hey-prefix, spelling variants, wake+trailing-query) + REJECT set (near-misses proving boundary safety) | Member 1 | Implement a wake-word matcher driven by config.WAKE_PHRASE: expand variants (single/multi-token), match token-level with word boundaries (no substring fires), support optional "hey/okay" prefix and wake+trailing-query. Commit a self-test with explicit ACCEPT and REJECT sets incl. deliberate near-misses. Acceptance: exit 0, all ACCEPT fire, all REJECT silent. Do not wire into the live pipeline in this task. | Self-test exit 0; all ACCEPT fire, all REJECT silent; near-misses prove boundary-safe matching. Offline-verified ONLY — live pass is WW-4. | DONE — 24 variants (11 single + 13 multi); 10/10 ACCEPT incl. wake+trailing-query, 8/8 REJECT incl. "see japan"/"logic jump" |  | config.WAKE_PHRASE; committed wake self-test output
WW-2 | Module | Canonical phrase ratification + config note (WAKE-CFG-1) | - Stakeholder gut-check on public wording BEFORE bench session [Member 3] - One-line config change to ratified spelling + dated comment [Member 1] - Re-run offline self-test (must be identical; STOP if any case flips) - Grep repo for old-spelling occurrences → report list, no doc edits | Member 3 → Member 1 | WAKE-CFG-1: set config.WAKE_PHRASE to the ratified spelling; add dated ratification comment above it. Nothing else — no variant/matcher/harness changes. Self-checks: (1) re-run offline self-test, expect identical pass; STOP if any case flips, do not adjust variants to force pass. (2) grep repo for old spelling in code/config, return list only. Evidence: config diff + self-test output + grep list. | Ratified spelling in config with dated comment; self-test identical pre/post; grep list returned for doc sweep. | IN PROGRESS — "Hey Cee Jap"/"Cee Jap" ratified by the sponsor and counsel 2026-07-27; WAKE-CFG-1 issued to Member 1, evidence pending | Member 1 (evidence) | decisions register entry 2026-07-27; config diff (pending)
WW-3 | Module | Bench-tuning harness + evidence capture (WAKE-LIVE-1) | - bench_wake_tuning.py: --mode wake (per-trial: speaker/distance/raw transcript/fired) + --mode soak (any fire = FALSE-ACCEPT) [Member 1] - --simulate flag: headless canned-transcript path proving CSV/report plumbing - bench_wake_report.py: speaker x distance hit-rates, missed-transcripts (dedup), verdict vs targets; INSUFFICIENT DATA below minimums - Imports PRODUCTION matcher — zero duplicated matcher logic | Member 1 | Build bench harness + report per WAKE-LIVE-1 spec: live path mic→STT→production matcher (import, never copy); wake + soak modes; append-only evidence/wake_bench_<date>.csv (utf-8-sig); report with per-speaker x distance table, deduped missed-transcripts (input for a SEPARATE reviewed variant add), pass/fail verdict, INSUFFICIENT DATA guard. --simulate for headless self-verification. Boundaries: do not touch matcher/variants/WAKE_PHRASE; flag, never fix, anything noticed in STT/filler. | Headless self-checks all pass (--help, simulate append, report, utf-8-sig round-trip, production-matcher import). Harness DONE ≠ wake word done. | DONE (offline-verified) — commit 487920d; 6/6 self-checks; simulate correctly yields INSUFFICIENT DATA on thin data |  | bench_wake_tuning.py; bench_wake_report.py; commit 487920d
WW-4 | Module | Live bench pass — THE acceptance gate | - >=3 speakers (Filipino-accented mix; incl. Member 2), each >=10 near (~1m) + >=5 far (~2-3m) attempts, both phrasings ("Cee Jap" and "Hey Cee Jap") [Member 3 runs, Member 1 supports] - 15-min false-accept soak with planted spoken near-misses - Misses → add OBSERVED transcripts to variant list via separate reviewed change; never loosen the matcher | Member 3 + Member 2 + Member 1 | Bench-day runbook: CJ_WAKE_WORD_ENABLED=1 python bench_wake_tuning.py --mode wake --speaker <name> --distance <near¦far>; then --mode soak --minutes 15 --speaker ambient; then python bench_wake_report.py. Needs pip install sounddevice. If misses cluster on specific STT transcriptions, capture them — the variant add is a SEPARATE reviewed change (re-run WW-1 self-test after). | Targets: >=90% per speaker near, >=80% far, 0 false-accepts over >=15 min soak, >=3 speakers minimum. Report must print PASS (not INSUFFICIENT DATA). | READY — awaiting demo-bench session (mic + speakers in room); run AFTER WW-2 evidence lands so the bench tests the ratified config | bench session; WW-2 | evidence/wake_bench_<date>.csv + wake_bench_summary_<date>.md (pending)
WW-5 | Module | Decisions: legacy variants + trailing-query handling | - Legacy "CJ"/"hey cj" still in ACCEPT set: keep-through-demo / prune-at-DEPLOY-1 — record either way [Member 3 + Sponsor] - Trailing query after wake currently DISCARDED (wake-then-listen): confirm as v1 behavior or spec forwarding into STT/router as first utterance [Member 3 + Sponsor] | Member 3 + Sponsor | (human decision — no CC prompt) Record both decisions in the decisions register; then a one-line CC task adds the config comment. Presenter script must match whichever trailing-query behavior is chosen. | Both decisions recorded with rationale + revisit date (DEPLOY-1). | OPEN — lean on record: keep legacy variants through August demo, prune at DEPLOY-1; trailing-query = wake-then-listen for v1 | Sponsor | decisions register (pending)
WW-6 | Module | Doc sweep — wake phrase across presenter scripts / signage | - Replace "Hey CJ" with "Hey Cee Jap" in presenter scripts (EN + Taglish), demo one-pagers, signage mockups [Member 3 + Member 2] - Script the interaction to match WW-5 decision (say wake → wait for acknowledgment → ask) | Member 3 + Member 2 | (Cowork) Using the WAKE-CFG-1 grep list plus the named docs, produce a changelist (file → old line → new line) for review; apply only after Member 3 approves. Do not edit legal-signed artifacts (NEW-6) — flag if the phrase appears there. | All public-facing materials say the ratified phrase; interaction script matches actual wake behavior. | OPEN — blocked on WAKE-CFG-1 grep list | WW-2 grep | doc changelist (pending)
OPERATIONS — recurring corpus & taxonomy work
OPS-1 | Ops | Corpus onboarding — NEW curated CJAP batch (recurring operation) |  | Member 2 → Member 1 | (recurring — follow CJP_Corpus_Onboarding_Runbook.md) Onboard a new curated batch: validate 15-column schema (utf-8-sig), normalise, append-only merge into corpus tree, re-chunk NEW docs only, update manifest. STOP on any schema violation; never mutate existing rows. Evidence: manifest diff + chunk counts. |  | DONE — batch-02 landed append-only: corpus now 1,109 docs / 9,865 chunks (refreshed 2026-07-27) |  | commit 0b486d2; CJP_Corpus_Onboarding_Runbook.md
OPS-2 | Ops | Full-corpus refresh: re-embed (bge-base) + centroid rebuild + orphan census |  | Member 1 | (recurring) Full-corpus refresh after onboarding: one re-embed (bge-base-en-v1.5 @768d) covering old+new, centroid rebuild, then promotion eval on the gold set (scope-aware grading; fabrication must stay 0). Tag a new arch-baseline vN only after Member 3 attestation. Evidence: provenance artifact + tag. |  | DONE — full-corpus re-embed + promotion; canonical baseline arch-baseline-v4.2, N=34 scope-aware grading, fabrication 0/40, Member 3 attestation + provenance artifact (refreshed 2026-07-27) |  | tag arch-baseline-v4.2 (9ef1f5c); provenance artifact
OPS-3 | Ops | Taxonomy expansion — add approved topic dimensions + rebuild |  | Member 3 + Member 2 → Member 1 | (gated on human sign-off) Draft taxonomy_expansion_PROPOSAL.md: candidate topic dimensions with per-dimension evidence (query logs, misses, corpus density). Present for Member 3+Member 2 sign-off BEFORE any centroid change. Expansion without recorded sign-off is out of scope. |  | AWAITING — OPS-2 now DONE; unblocked pending expansion proposals + human sign-off. Expand ONLY evidence-backed dimensions. | proposals + sign-off | taxonomy_expansion_PROPOSAL.md (pending)
CORPUS MAINTENANCE — Sept 2026: data-flow audit, correction batch-03, new-material batch-04 (runbook: Project Plan v2 › Data Flow + Corpus Expansion)
CM-1 | Maint | Corpus data-flow audit (source → enriched row → corpus → index) | - Traced the live build path: data/text/<ID>.md + 4 normalised xlsx → generate_corpus_from_xlsx.py → corpus/ → chunks → indexes [Member 3 + Claude] - Counted what is in the corpus and the next free ID per series [Claude] - Found defects D-1…D-6 (Data Flow sheet §6) [Claude] | Member 3 | (Cowork, done) Audit the corpus data flow end to end and record it on the Project Plan's Data Flow sheet. | Documented flow + inventory: 1,109 docs before retirement (785 columns · 135 book chapters from 10 books · 154 speeches · 35 biography chapters). | Done |  | CJAP_Robot_Project_Plan_v2.xlsx › Data Flow
CM-2 | Maint | Generator guard: strip YAML front matter from source .md | - Added strip + report of a leading '---' block in scripts/generate_corpus_from_xlsx.py [Claude] - Verified: full regenerate before the change matched the live corpus; after it, ONLY the 22 affected chapter .md files changed, and only by losing the header [Claude] | Member 1 | (executed) Content-aware regen diff, CRLF-normalised, in a scratch folder — live corpus untouched. | 22/22 affected docs fixed in regen; 0 other files changed. Takes effect in the live corpus at batch-03. | Done |  | scripts/generate_corpus_from_xlsx.py (uncommitted — D-6)
CM-3 | Maint | Retire 5 summary-only / duplicate docs without renumbering | - BA040, BC009, BC010, BD018: no source text in data/ or online [Claude] - SA085: duplicate of SB085 [Claude] - Register row per ID; generator skips them; files moved to data/retired/corpus/ (nothing deleted) [Claude] | Member 1 | (executed) CE-18 procedure — see Corpus Expansion. | Corpus now 1,104 docs (785 · 131 · 153 · 35). Regen: summary-fallback 0; every other file identical to live. 27 chunks remain in the index until batch-03. | Done |  | data/csv/retired_doc_ids.csv · data/retired/corpus/
CM-4 | Maint | Correction batch-03 — fix D-1, D-2, D-3 as ONE batch, before any new material | - Fix the 22 dates in cjp_books_curated_normalized.xlsx [Member 2] - Regenerate; content diff must show only the 22 fixed + 5 retired docs [Member 1] - Re-pin, re-chunk, full re-embed (bge-base @768d), retag against the CURRENT 34 topics [Member 1] - Promotion eval vs the standing baseline; attest; tag [Member 1 → Member 3] | Member 1 | Run CE-17 for batch-03 using batch-03/correction_list.md (22 date fixes + 22 front-matter regenerations + 5 retirements). STOP if any doc outside the list changes. | Changed-doc set == correction list; fabrication 0; no regression on pre-existing gold queries; attested; new arch-baseline tag. | Not started | Date decision for D-2 (proposed 2001-12-01, month precision)
CM-5 | Maint | New-material batch-04 — intake + source .md + enrichment (can start now) | - CE-1/1a/1b for 18 columns (25 May – 21 Sep 2026): CA530–CA543, CB020–CB021, CD030–CD031 — .md + enriched rows, C2 QA 18/18 pass [Member 2 + Claude] - CA529 (Phase-1 'Rule of, or by, law') WITHDRAWN: verified as Michael L. Tan's 'Pinoy Kasi' column, not CJP. ID void; files in batch-04/_rejected/ [Member 2] - B0 split of 8 books → 167 chapters; B1 intake done (BA051–BA107 · BB009–BB044 · BC023–BC046 · BD027–BD071 · BE030–BE034) [Member 2 + Claude] - Next: review themes and the 21 long chapters, then B2 (.md) and B3 (enrichment) [Member 2] | Member 2 | Follow Corpus Expansion CE-1 → CE-3 for batch-04. Nothing is merged into the pinned sheets until batch-03 is promoted. | 18 columns ready (QA passed, 10-row sign-off pending). 167 book chapters split and registered; no duplicates; 185 rows staged in batch-04/intake_manifest.csv. Nothing merged into data/ or corpus/ yet. | In progress | Theme + long-chapter review; then B2/B3; merge waits on CM-4 (batch-03) | batch-04/ (intake_manifest.csv · columns_enriched.xlsx · qa_columns.md · intake_books_report.md · book_split/ · data_text/)
CM-6 | Maint | Merge + promote batch-04; then sync the delivered repo | - CE-4 … CE-14 on top of the batch-03 baseline; CE-8 decides retag / expand / rebuild [Member 1 + Member 3] - Recover or rewrite the normalisation script (D-4) [Member 1] - Commit and push both batches; bring Final Project Folder up to date (D-5, D-6) [Member 1] | Member 1 | Run CE-4 onwards for batch-04, then CE-15: refresh every quoted corpus / chunk / topic count. | Promoted baseline including batch-04; counts refreshed everywhere; both repos clean and pushed. | Not started | CM-4 and CM-5
CM-7 | Maint | Column source fix: book H1 titles aligned to the sheet titles | - 111 data/text/B*.md had an H1 that did not match the sheet Title, so the generator left it in the body [Member 2] - H1 replaced with '<Book> -- Ch. N: <Title>'; originals backed up with a change_log.csv [Member 2] - Regenerate check: 97 corpus docs lose a duplicate heading; nothing added; 0 .json changes [Claude] | Member 2 | (executed) Verified by regenerating to a scratch folder and diffing against the live corpus. | Sources fixed and logged (defect D-10). The corpus and index still carry the duplicate heading until batch-03 regenerates. | Done |  | data/text/B*.md · batch-04/backup_data_text_books_2026-09-23/change_log.csv
CM-8 | Maint | Prompt pack revised after the first column run | - C0/C1/C2 updated: paste without the template, URL lookup from the byline pages, printed typos kept and flagged, four confidence values [Member 2 + Claude] - Plan v2 Intake Prompts sheet updated to match, with per-step status [Member 2] - Plan v2.5: ID register advanced, D-8 closed, D-10 added, contract allows a plain title line [Claude] | Member 2 | (Cowork) Keep the prompt files and the Intake Prompts sheet identical whenever either changes. | Prompts and plan agree; the 23 Sep run is reproducible from them. | Done |  | batch-04/BATCH-04_*_PROMPTS.md · CJAP_Robot_Project_Plan_v2.xlsx (Intake Prompts)
Lead key: Member 1 = code/implementation . Member 2 = support/curation/docs . Both = shared with subtask split shown.
Note on C7: Re-scoped: subset is now an EVAL-TIME ALLOWLIST (consumed at W1.5/W3), not the chunk input - W1.4 chunks the FULL corpus, so subset re-freezes no longer trigger re-chunking. v4 supersedes v3(95)/v2(125, broke cap)/v1(25). Forced-list re-derivation + relabels per the W1.3 audit memo. Does NOT block W1.4 - runs in parallel; only the pin step (W1.4) is a shared touchpoint.
Note on C8: Re-scoped to FULL-corpus chunking + corpus pin. Why: the corpus/ tree is generated from the stale 80-doc CSVs, so 89/95 pilot docs have no file to chunk - regenerate from the canonical xlsx first. Full-corpus chunking decouples the stable chunk store from the churning subset (v3->v4->...), and W1.7 needs the full corpus processed anyway. PIN (snapshot + verify_pin) makes the frozen set verifiable against drift. Runtime index (W1.5) + eval stay subset-only.
Note on C12: Re-scoped from 'tune' to 'BUILD'. Evidence from W1.1: the new architecture (centroids/numpy/RRF, Haiku removal) is NOT implemented anywhere; the live path is the documented Haiku->Sonnet baseline. W1.8 is therefore a build, not a tuning pass. Tail order: W1.8 -> W1.9 -> W1.11 -> W1.10.
Note on C15: NEW row. pilot-baseline (W1.1) was tagged on the OLD architecture (Haiku in path, un-slimmed payload) - anchoring any latency/cost delta on it would be wrong by the Haiku-round-trip + slimming margin. arch-baseline is the clean post-W1.8 anchor. Runs after W1.8 + W1.9, FEEDS W1.10 (memo can't finalize latency targets until these numbers land).
Note on F5: Note (post-run): suggested base 'feat/topic-map-coverage' did NOT exist; base chosen on evidence = pre-wake-word-integration @07a8b8d. The 'locked new architecture' (centroids/RRF/Haiku-out) was DESIGN-ONLY at W1.1 - config surface landed, implementation is W1.8.
Note on H6: Normalized xlsx canonical; W1.6 confirmed 1,089 keyword cells JSON-parsed, 0 fallback.
Note on H7: v4 allowlist; 95/95 resolve -> 827 chunks.
Note on H8: 8,887 chunks; doc store; sha256-pinned; verify_pin PASS.
Note on H9: pilot_dense.npy 827x1024 cuda_fp32; regenerated/sliced in W1.7 (parity 1.0).
Note on H10: BM25 + atomic dict; complementarity proven; 827 aligned; case short-form fix in W1.8.
Note on H11: 34 topics; merge 0.95/floor 0.68 locked; 0/1089 doc-orphans; 95/95 tagged; pushed dec95bd.
Note on H12: Haiku-out (0 pre-comp LLM); RRF + soft-prior; grounded e2e; 277fc90 (+W1.8b transport 2fb8920).
Note on H13: Warmed baseline native_sdk; TTFT ~1.2s, e2e ~8s, ~$0.017/q; 340b843 (n=10 stand-in).
Note on H14: Decisions memo drafted (DOCX); ratified at team meeting (tech lead + full team go-signal). Confirm meeting date + targets in Pilot Metrics.
Note on H15: arch-baseline tagged (frozen set sha 65492b65, n=40); p50/p95+TTFT+cost captured; native_sdk; commit caa3c8c, tag pushed 5c86d65. Week 1 closed.
Note on H16: Streamed composer + trailing ENVELOPE; COMPOSER_MAX_TOKENS=640 (0 truncations); timeouts/retries/graceful degradation; TTFT -21%/-43% vs arch-baseline; commit 3ef2e05. Sheena voice smoke-test still owed (manual).
Note on H17: Payload slimming: top_k/char-budget config params; lean contract formalized (enrichment excluded); input tokens -48.7% at top_k=6, 0 grounding losses; default behavior-preserving (top_k=12). top_k=6 validated & ready to bank (-32% cost). commit 0aedbd7.
Note on H18: Prompt caching mechanism ALREADY ACTIVE (W1.9 showed 4,411 cached voice-card tokens/q). Task = formalize + verify cache boundary (nothing per-query leaking into static prefix).
Note on H20: Soft-prior theme-as-control-signal + thresholds already built/locked in W1.7-W1.8. Remaining = tuning (W3.4).
Note on H22: REVISION (scorecard): now the HIGHEST-VALUE latency fix. Composer = ~95% of latency (p50 11.7s of 12.3s). Streaming generation -> TTS sentence-by-sentence takes FELT latency ~12s -> ~3s at ZERO quality cost (changes when audio starts, not what is said). Also fold in keep-alive/warm-model (48s cold load paid once at startup, never by a visitor). Elevate above other latency work. See Latency Remediation & Exhibit-Gate Plan.
Note on H25: REVISION: BLOCKING for any public demo. E_Quality (6/6) and faithfulness/hallucination/citation rows are BLANK - retrieval recall (0.91) is proven but answer GROUNDEDNESS is unmeasured. Author Gold_Question_Set reference answers (harness exists, must-cite doc_ids pinned; reference answers blank).
Note on H26: REVISION: BLOCKING for any public demo. Measure faithfulness (>=0.95), high-stakes hallucination (=0), persona similarity (>=0.75), factual accuracy on the Gold set. A CJ robot that hallucinates a ruling fails worse than a slow one. This gate - not latency - is what should block the exhibit. Unblocks the W3.4 model/length trades.
Note on H28: REVISION: retrieval ALREADY PASSES (Recall@5 0.91, MRR 0.8, nDCG 0.83) - the retrieval sweep is now confirmation, not a hunt. Primary W3.4 work shifted to LENGTH + MODEL trades, each GATED on the W3.2 quality baseline and re-scored on faithfulness/persona before adoption. Do NOT cut max_tokens or swap model before W3.2. Also: bank top_k=6 here (validated in W2.2).
Note on H30: NEW (revision): the OOS gate was a parked known-open item living only in task comments; promoted to a tracked row. PRE-DEMO BLOCKER. Sequence: alongside W3.1/W3.2 (needs the labeled set), before any public-facing use. Was uncalibrated at W1.11 baseline (recorded 40/40 in-scope, incl. the 2 oos probes) - calibrating it is a measurable W3.x win vs arch-baseline.

## Pilot Metrics
Pilot Metrics - targets + baseline in Week 1, results in Week 3
Metric | Definition | Target (set W1) | Baseline | Pilot result | Pass?
End-to-end latency p50 | Median total response time across the eval set. | <= ~8.0s p50 (provisional, n=10) | 8044.8 ms (8.0s) - W1.9 warmed | [ ] | [ ]
End-to-end latency p95 | 95th-percentile total response time (worst-case paths show here). | <= ~8.9s p95 (provisional, n=10) | 8928.2 ms (8.9s) - W1.9 warmed | [ ] | [ ]
Time-to-first-token (TTFT) | First-token latency, measured separately from total - streaming can mask slow generation. | p50 ~1.2s / p95 ~2.1s (provisional, n=10) | p50 1207 / p95 2087 ms - W1.9 warmed | [ ] | [ ]
Time-to-first-audio (TTFA) | First audio out for the voice front-end (stream -> sentence-chunk -> TTS). | TBD - set when TTS front-end exists (W2.1) | not measured (no voice/TTS pipeline yet) | [ ] | [ ]
Per-stage latency | Time in input gate / router / retrieval / composer. | hold (path is composer-bound, ~97%) | p50 ms: gate 0.0 / router 164.6 / retrieval 83.2 / composer 7790.2 - W1.9 | [ ] | [ ]
Fabricated citations | Citations not supported by the corpus. Target = 0. | 0 (release requirement) | TBD - W3.x eval harness | [ ] | [ ]
Grounding-fidelity score | Eval-set score for answers grounded in retrieved chunks. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
In-voice register match | register_used vs expected on the eval set. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
AI-governance retrieval | Whether the known retrieval miss is now surfaced. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Out-of-scope handling | Off-taxonomy queries correctly thresholded + declined. | TBD - needs OUT_OF_SCOPE_THRESHOLD calibration (W3.x) | TBD (threshold 0.15 provisional/uncalibrated) | [ ] | [ ]
Routing accuracy | Predicted theme/topic vs the gold doc's topic on the eval set. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Retrieval recall@k | Share of eval queries with the gold passage in top-k (soft-prior should hold this high even when routing errs). | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Cost per query | Avg API cost per response - log INPUT vs OUTPUT and CACHED vs UNCACHED; should fall vs baseline. | <= ~$0.017/query cached (provisional) | cached $0.0169 / uncached-equiv $0.0288; caching saves $0.0119 - W1.9 | [ ] | [ ]
Output tokens per answer | Average answer length in tokens - drives cost/latency regardless of payload size. | <= 300 (MAX_TOKENS cap) | median 261, range 131-300 (2 of 10 hit the 300 cap) - W1.9 jsonl | [ ] | [ ]
Theme-A disclaimer present | Share of law-themed responses with the disclaimer. Target = 100%. | TBD - W3.x payload sweep | current locked: tau=0.3, min_k=3, max_k=12, max_tokens=300, lambda=0.25 (untuned) | [ ] | [ ]
Payload knee config | tau / min_k / max_k / chunk budget / max_tokens where quality is flat but cost/latency drop. | dynamic (knee found in W3.x) | 12.0 - all 10 queries saturated MAX_K=12 (cutoff hit ceiling) - W1.9 | [ ] | [ ]
Chunks per query (dynamic) | Avg chunks admitted by the relevance cutoff (score >= tau*top_score, bounded min_k..max_k). | tuned in W3.4 bake-off | locked (untuned): RRF_K=60, topic-bias lambda=0.25 | [ ] | [ ]
Dense/sparse fusion weight | Tuned RRF weighting + topic-bias lambda. | TBD - W3.x eval harness | TBD - no labels yet | [ ] | [ ]
Register-classifier accuracy | Deterministic register vs hand labels. | TBD - gate set in W2.1 | caching present (voice card ephemeral); hit-rate not yet measured | [ ] | [ ]
Prefix cache hit rate | Share of composer calls hitting the cached prefix. | < ~10% (release GATE) | N/A - expand-on-demand built in W2.1 | [ ] | [ ]
Expand-on-demand fire rate | Share of queries needing the whole-doc fallback. Release GATE: fix upstream if > ~10%. | [ set ] | [ ] | [ ] | [ ]
Wake-word success (near ~1m) | Share of live wake attempts that fire at conversational distance. Live bench per WW-4; >=3 speakers, >=10 attempts each, both phrasings ("Cee Jap" / "Hey Cee Jap"). | >= 90% per speaker (release gate for kiosk) | offline matcher self-test 10/10 ACCEPT (text-level only — not a live proxy) | [ ] | [ ]
Wake-word success (far ~2-3m) | Share of live wake attempts that fire at kiosk distance. Same bench session; >=5 attempts per speaker. | >= 80% per speaker (raise to 90% if far is the primary visitor position — confirm bench layout with Sponsor) | not yet measured (live bench pending, WW-4) | [ ] | [ ]
Wake false-accept rate (soak) | Wake fires during normal conversation near the mic, incl. planted spoken near-misses ("see Japan", "the Japanese economy"). Soak mode flags any fire as FALSE-ACCEPT. | 0 over >= 15 min soak (release gate) | offline REJECT 8/8 incl. near-misses (text-level only) | [ ] | [ ]
Blue cells are inputs for the team to fill in.