PROJECT COMPLETION SUMMARY

AI-Powered Conversational Robotic Exhibit

CJAP Robot  ·  Foundation for Liberty and Prosperity  ×  Supervaise Inc.

| Project | AI-Powered Conversational Robotic Exhibit (CJAP Robot) |
| --- | --- |
| Client | Foundation for Liberty and Prosperity (FLP) |
| Delivered by | Supervaise Inc. |
| Subject | Chief Justice Artemio V. Panganiban — institutional legacy, Liberty and Prosperity |
| Hardware | Reachy Mini robotic unit |
| Kickoff | 28 April 2026 |
| Status | Showcase delivered. All six phase gates closed. |
| Report date | 20 September 2026 |

# 1 · Purpose of this document

This summary records what was committed at kickoff, what was delivered, what was added at the client's request, and what remains open after the showcase. It reconciles the delivered system against the approved scope in the kickoff deck and the minutes of 28 April 2026, so that FLP and Supervaise hold the same account of the engagement at handover.

Status entries are drawn from the project's own evidence chain — tagged baselines, evaluation results and committed artifacts.

# 2 · Phase gates

All six gates defined in the kickoff deck are closed.

| Phase | Go / No-Go gate | Status |
| --- | --- | --- |
| 1 · Discovery, alignment & procurement | FLP confirms scope and materials availability | Done |
| 2 · Knowledge base build | FLP approves the curated knowledge base | Done |
| 3 · Prototype development | FLP accepts execution of approved scope on the prototype | Done |
| 4 · Conversational scripting & refinement | FLP signs off on final scripts (2 revision rounds) | Done |
| 5 · Testing & stakeholder preview | CJ Panganiban and Dir. Barbosa approve | Done |
| 6 · Completion guarantee | Successful event deployment | Done — showcase delivered |

# 3 · Scope delivered

| Commitment at kickoff | Status | Note |
| --- | --- | --- |
| One conversational robotic prototype | Delivered | Showcased to stakeholders |
| Reachy Mini hardware integration | Delivered | Record which contingency shipped — Plan A units or a fallback |
| Conversational AI grounded by retrieval | Delivered | Hybrid dense + keyword retrieval across 34 topic dimensions |
| AI provider | Changed | Built on Claude with local embeddings rather than ChatGPT; anticipated by the kickoff action item on provider cost comparison |
| Curated knowledge base | Exceeded | 1,109 documents against a contracted cap of 50 paper documents |
| English output, Taglish input | Delivered | English-only output held throughout |
| Voice interaction | Delivered | Streamed speech with sentence-boundary handoff to synthesis |
| Approved scripts, fallbacks, boundaries | Delivered | Calibrated scope gate, deterministic disclaimer, locked decline wording |
| Prototype testing & stakeholder preview | Delivered | Pilot report and readiness verdict issued before the showcase |
| Handover guidance | Delivered | Turnover document, internal playbook and handover deck |

# 4 · Client-requested additions

Two components sit outside the original written scope. Both originated with the Chief Justice and both proved central to how the exhibit lands on a visitor.

| Addition | Why it was requested | Status |
| --- | --- | --- |
| Licensed voice clone of CJ Panganiban | Requested by the Chief Justice himself. Hearing his own voice is what makes the exhibit feel like him rather than merely about him — it carries the emotional connection the kickoff flow diagram places at the centre of the visitor experience. | Delivered |
| Wake word — “Hey Cee Jap” | Requested so a visitor addresses the robot by name rather than triggering it by proximity. Being answered when called is part of the sentiment of the interaction, not a technical convenience. | Delivered |

The voice clone ships with a local fallback voice for outages, and with pre-rendered fixed lines — greetings, bridges, declines and the disclaimer — cached in the cloned voice so they play instantly. The wake phrase was ratified by the sponsor and counsel before the bench work, and is held in a single configuration value so it can be changed without touching code.

# 5 · What was built

| Artifact | Form |
| --- | --- |
| Retrieval and composition pipeline | Live system, tagged baseline, attested |
| Curated corpus | 1,109 documents / 9,865 chunks, hash-pinned with a verification script |
| Topic map | 34 centroid dimensions, independence-checked, with an orphan census |
| Evaluation harness and gold set | 40 labelled queries with expected sources |
| Wake-word module | Matcher, offline self-test and bench harness — reusable on future builds |
| Voice clone and pre-rendered lines | Greetings, bridges, declines and disclaimer, cached |
| Maintenance interface | Key-gated operator surface, 12 cards |
| Pilot report and readiness verdict | Word documents |
| Client one-pagers | Four: pipeline, cost and corpus, robot operation, interface design |
| Turnover document, internal playbook, handover deck | Word and PowerPoint |
| Architecture diagrams | Three: overall pipeline, validity gate, cost and latency |
| Project plan and pilot tracker | Excel |

# 6 · Measured results

Every figure below comes from a tagged baseline run against the 40-query evaluation set.

| Measure | Result | What it means |
| --- | --- | --- |
| Fabricated citations | 0 of 40 | No answer cited material it was not given |
| Retrieval recall | 0.735 at 1 · 0.971 at 5 | The expected source reached the composer in almost every case |
| Corpus scale | 1,109 docs · 9,865 chunks | Well beyond the 50-document contractual floor |
| Topic dimensions | 34 | Rebuilt from scratch, independence-checked |
| Time to first token | 1.53 s (median) | How quickly the answer begins forming |
| Time to first audio | ~4 s live | Dominated by transcription, not by the model |
| Cost per question | $0.0155 cached | One model call; retrieval and routing run at no cost |
| Model calls before composition | 0 | Routing is deterministic code, not a second model |

# 7 · Running costs after handover

API subscriptions and cloud hosting were a named exclusion at kickoff and pass to FLP on completion. Three components are metered per use. Rates below are vendor list prices checked on 20 September 2026 and exclude tax; confirm them before budgeting.

| Component | Provider and rate | Per question |
| --- | --- | --- |
| Transcription (speech to text) | ElevenLabs Scribe v2 Realtime — $0.39 per audio hour | $0.0009 |
| Composition (the answer itself) | One model call — measured on the delivered system | $0.0155 |
| Speech (text to speech) | Fish Audio s2-pro — $15 per million UTF-8 bytes | $0.0165 |
| Total per question | Assumes an 8-second question and a ~1,100-character spoken answer | ~$0.033 |

Speech is the largest single line. Synthesising the answer costs slightly more than generating it, which means the cost of the exhibit is governed by how much it says, not by how hard it thinks. Fixed lines — greetings, bridges, declines and the disclaimer — were rendered once and cached, so they cost nothing at runtime.

Choice of speech provider

| Speech provider | Rate | Per answer | Effect on the total |
| --- | --- | --- | --- |
| Fish Audio s2-pro | $15 per million bytes | $0.0165 | ~$0.033 per question |
| ElevenLabs Flash / Turbo | $0.05 per 1,000 characters | $0.055 | ~$0.071 per question |
| ElevenLabs Multilingual v2 | $0.10 per 1,000 characters | $0.110 | ~$0.127 per question |

The voice clone itself is a separate consideration from the per-character rate: changing speech provider means re-cloning the voice, obtaining consent for the new vendor, and re-rendering every cached line. It is a client decision, not a configuration change.

Monthly projection

| Questions per day | Per day | Per 30 days | Per 30 days if the higher-cost voice is used |
| --- | --- | --- | --- |
| 100 | $3.29 | $98.70 | $214.20 |
| 250 | $8.23 | $246.75 | $535.50 |
| 500 | $16.45 | $493.50 | $1,071.00 |
| 1,000 | $32.90 | $987.00 | $2,142.00 |

These figures are straight multiplication of the measured per-question cost by an assumed volume. They exclude hardware, power, connectivity and staff time.

Two cautions for whoever holds the subscription

- The microphone stream must stay closed until the wake word fires. Transcription is billed per audio hour, not per question, so an always-open stream costs roughly $9.36 per day per robot — about $140 a month even on a twelve-hour day — regardless of how few questions are asked. The delivered system gates the stream on the wake word, which is what keeps this line near zero.

- The kickoff estimate of roughly $20 to $50 a month covered a text-only assistant. It predates the voice clone and the wake word, and it does not reflect a speaking exhibit. At moderate visitor traffic the realistic figure is in the low hundreds per month, and FLP should budget against the table above rather than the original estimate.

# 8 · Open after the showcase

None of the following blocks the exhibit. They close out the engagement.

| Item | Why it matters | Owner |
| --- | --- | --- |
| Milestone 4 certificates | Contracted documents: two-month support and maintenance, training materials and attendance, operational handover, and final acceptance | Supervaise PM |
| API subscription handover | A named exclusion at kickoff — FLP owns running costs after completion. Section 7 gives the current rates and the monthly projection | Supervaise PM → FLP |
| Capture showcase evidence | Real visitor questions, live wake performance and actual response times were generated on the day and are not yet recorded anywhere | Technical Manager |
| Post-showcase decisions | Legacy wake variants were flagged for pruning at deployment; trailing-query handling was left as wake-then-listen for this version | Technical Manager |
| Provider change on the record | The approved scope names ChatGPT; the delivered system runs on Claude. Worth a written note so the record matches the build | Supervaise PM |

# 9 · Notes for the record

- The wake phrase should not be revised. It has been spoken in public by the exhibit, it works, and the sponsor ratified it. Spelling in documents can be corrected without touching the spoken phrase.

- The showcase is the most valuable untested material the project has. Real visitors asked real questions, at real distances, in real accents — none of which any synthetic evaluation set contains. If recordings or logs survived, they are worth more than the next several rounds of authored test items.

- The knowledge base can grow without rebuilding the system. A documented expansion runbook covers adding new columns, speeches or books, and decides in one step whether the topic map is re-tagged or rebuilt.

- The architecture carries forward. Retrieval, composition, the validity checks and the wake-word module are corpus-agnostic, which is what makes the phased museum buildout described at kickoff a continuation rather than a restart.

Prepared by:

_________________________________

John Anthony C. Jose, Ph.D.

Chief Technology Officer

Supervaise Inc.