## Slide 1
CJAP — Conversation Robot
Chief Justice Artemio V. Panganiban, in his own voice and corpus
Project handover
Supervaise Inc. → Foundation for Liberty and Prosperity
Repository: github.com/Supervaise-Inc/CJAP · pi/deployment-snapshots @ 2545882 (2026-08-31)
20 September 2026
Supervaise Inc. — Unlocking Possibilities Together
Notes: Handover of the CJAP conversation robot. Everything presented traces to the repository at the commit on this slide, or to a named pilot document. Figures are labelled Target or Measured throughout. Slides carrying [TO CONFIRM] are deliberate: those numbers were never measured and are not estimated here.

## Slide 2
What was built
One sentence, one picture
A desktop robot that answers questions as the Chief Justice, from his published writing.
REACHY MINI
face · ears · mouth
on-device, offline
CURATED CORPUS
79 documents
35 topics
CLAUDE
Haiku 4.5 routes
Sonnet 4.6 composes
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
2
Notes: Two paid Claude calls per turn. The voice is a clone of the Chief Justice's own, licensed through ElevenLabs. The robot never claims to be a machine and never invents a view he did not publish. Three parts: the robot is embodiment only; the corpus is the ground truth; Claude does routing and composition. The persona rule (2026-08-09) is that it answers in the first person AS the Chief Justice and deflects machinery questions with humour — it never describes itself as an AI. That is enforced in three places: the voice card, a zero-cost rule gate before audio exists, and an asynchronous Haiku audit.

## Slide 3
Pipeline architecture
One question, end to end · two Claude calls
VISITOR ▌ ON-ROBOT · local · no cost ▌ CLOUD · paid per call
────────────────▌───────────────────────────────────▌──────────────────────────
"Hi Cee-Jap" ──►▌ [1] WAKE openWakeWord ▌
▌ hi_see_jap.onnx · thr 0.08 ▌
asks question ►▌ [2] CAPTURE mic → 1.5s silence ──▌──► [3] STT OpenAI
▌ ▌ gpt-4o-mini-transcribe
▌ [4] NAME REPAIR + ANSWER GATE ◄────▌───────────┘
▌ [5] CANNED? ─yes─► cached clip ─► END (zero Claude calls)
▌ │ no ▌
▌ ├────────────────────────────▌──► [6] ROUTER ══ CALL 1
▌ │ ▌ Claude Haiku 4.5
▌ [7] RETRIEVAL 35 topics → docs ▌ max 160 tokens out
▌ │ context ≤ 5,000 tokens ▌
▌ [8] FILLER plays ─────────────────▌──► [9] INFERENCE ══ CALL 2
▌ │ sentence by sentence ▌ claude-sonnet-4-6
▌ │ ▌──► [10] TTS ElevenLabs
▌ │ ▌ LeM5jaQwKcHJtzmSBNlA
◄── PLAYBACK ──▌──────┘ + async Haiku audit ▌ fails open ► OpenAI
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
3
Notes: Call 1 is the router (Haiku 4.5, claude-haiku-4-5-20251001), capped at 160 output tokens because every router token delays speech. Call 2 is the composer (Sonnet 4.6, claude-sonnet-4-6), streamed sentence by sentence so the robot starts speaking before the answer is finished. The filler plays during the gap so the visitor never hears silence. Two more Haiku calls — the dynamic filler and the fidelity audit — sit off the critical path and add no delay. A canned match short-circuits the whole thing with zero Claude calls.

## Slide 4
Component stack
What runs locally, what is a paid API, and what happens when it fails
Stage | Component (verbatim) | Local / API | Fallback
Wake | openWakeWord hi_see_jap.onnx | Local | Operator force-listen from /maintain
STT | OpenAI gpt-4o-mini-transcribe | API | None wired. Local switch exists, unused
Gates | postprocess.py · answer_gate.py | Local | Fail open — turn proceeds
Canned | canned_answers.json | Local | No match → normal path
Router | Claude Haiku 4.5 | API | Truncated JSON → anchor routing
Retrieval | topic_map.json → whole documents | Local | No match → theme-level documents
Inference | Claude Sonnet 4.6, streamed | API | Credit/network loss → in-voice degraded line
TTS | ElevenLabs clone LeM5jaQwKcHJtzmSBNlA | API | Fails open to OpenAI TTS
Audit | Claude Haiku, asynchronous | API | Fails open; composer is primary safety
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
4
Notes: Read this as the resilience map. Everything local keeps working without internet: the wake word, the gates, the canned answers, retrieval. Everything marked API stops without internet or credits. The single weakest link is STT — it has no automatic failover. A local faster-whisper backend exists as a config switch (LOCAL_STT_MODEL) and was recommended by the pilot as the main latency fix, but was never wired. Piper is not in the live path; it appears only as a legacy laptop-only setting.

## Slide 5
Knowledge base
79 documents · 35 topics · curated
▪ 64 columns + 15 speeches = 79 documents
▪ 35 curated topics, four tiers
▪ No vector search — curated lookup, not similarity
CURATION PIPELINE
data/csv + data/text
↓ generate_corpus_files.py
corpus/**/*.md + *.json
↓ build_topic_map.py
corpus/voice/topic_map.json (35)
Routing accuracy
96.7% Measured against a Target of ≥85%.
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
5
Notes: Each document is a paired .md text file and .json metadata file. Curated from a 15-column spreadsheet with source text matched per document. One biography row was skipped: no single publication date, and placeholders are forbidden. The 96.7% figure comes from the repository's own 30-question smoke set, reports/smoke_test_summary.json. The design bet was that a hand-curated index beats statistical search on a small, dense corpus. The smoke set measured 96.7% primary-routing pass against an 85% target, with zero fabricated citations. One documented routing miss exists — the JMSU question — recorded in docs/lessons/LL-011. Keep that question off a live stage. Note the 1,109-document corpus you may have heard about is a different repository; see the second-to-last slide.

## Slide 6
Robot operating cycle
Every step has a timeout, a barge-in and an error path
Step | Timeout / barge-in / error path | Duration
Idle | Alive gesture every 10 s · no timeout · service starts at boot | Measured indefinite
Wake detected | Score ≥ 0.08 in a 2.5 s window · miss → operator force-listen | Measured 0.33–0.6 s
Listening | Closes after 1.5 s silence · under 0.4 s of speech is discarded | Measured 1.6–3.1 s
Transcribing | “Ah.” plays · no STT failover · offline → not-connected clip | Measured 1.2–1.6 s
Routing | Truncated JSON → anchor routing · canned match skips it | [TO CONFIRM] on robot
Generating | Filler holds 1.2 s · no credits → in-voice degraded line | [TO CONFIRM] on robot
Speaking | Barge-in: wake phrase cuts playback · TTS → OpenAI fallback | Measured first audio 4.9–6.2 s
Return to idle | Follow-up window disabled · next question needs a fresh wake | Measured immediate
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
6
Notes: The visitor-felt number is 4.9 to 6.2 seconds from the end of their question to the first spoken word — measured 2026-08-21 after the latency work. Before streaming it was 15 to 20 seconds. The README target is 4 seconds end to end, so this is close but not met. Two stages on this slide have never been measured on the robot itself: routing and generating. They are logged per turn to the maintenance page; nobody has summarised them. That is an open item with an owner.

## Slide 7
Untethered runtime
The honest gap
[TO CONFIRM: untethered runtime never measured — requires a timed discharge test | owner: hardware]
No battery or power figure exists here.
▪ Repository search found nothing
▪ To close it: one timed discharge, one timed recharge
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
7
Notes: No battery capacity, runtime on a full charge, recharge time or idle-versus-active power figure exists anywhere in the repository. Figures here are not inferred from datasheets. The search covered battery, charge, discharge, mAh, watt and power-draw terms and found nothing but corpus prose. Datasheet figures are refused here because they cannot account for the mic array, the always-on wake model, Bluetooth audio or the motors. To close it: full charge, run the normal turn cycle to shutdown, log wall-clock runtime and turn count, then a timed recharge — one afternoon of work. This slide is deliberately empty of numbers. Every figure that belongs here would have been a guess, and a plausible guess on a handover slide is worse than a blank. If the client plans to run the robot away from mains power — at a museum stand, for example — this test must happen before that commitment is made. It is cheap: one timed discharge and one timed recharge.

## Slide 8
Cost model
Per turn, and at volume
Stage | Cost per turn | Basis
Router (Haiku) | ≈$0.001 | Derived
Inference (Sonnet) | ≈$0.023 | Derived
Filler + audit (Haiku) | ≈$0.002 | Measured
STT (OpenAI) | [TO CONFIRM] | metered, never priced
TTS (ElevenLabs) | [TO CONFIRM] | 300–450 credits/answer
Anthropic total | ≈$0.025 | vs Target ≤$0.02
Turns / month | 100 | 1,000 | 10,000
Anthropic only | ≈$2.50 | ≈$25 | ≈$250
Blended | [TO CONFIRM] | [TO CONFIRM] | [TO CONFIRM]
Do not quote a total turn cost yet.
Only Anthropic is priced. Repeat questions are free — audio is cached locally.
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
8
Notes: All three providers are metered in app/usage_meter.py; only Anthropic has been converted to dollars. Canned answers cost nothing at all. The $0.025 figure is derived, not measured directly: the robot logged 8 composer calls across 79,760 tokens at roughly $0.20 in one service session. It is Anthropic only. The bill is input-heavy by design — every answer carries the persona and the retrieved documents in with it — and prompt caching already bills cached input at one tenth. Cost is not the problem here; at a thousand questions a month this is roughly twenty-five dollars.

## Slide 9
Performance
Target versus measured — and what was never measured
Metric | Target | Measured | Verdict
Router accuracy | ≥85% | 96.7% | Met
Fabricated citations | 0 | 0 across all graded runs | Met
End-to-end to first audio | ≤4 s | 4.9–6.2 s | Not met
Cost per turn (Anthropic) | ≤$0.02 | ≈$0.025 derived | Not met
Speech-to-text latency | — | 1.2–1.6 s | Measured
First-sentence synthesis | — | 1.7–2.5 s | Measured
Never measured on the robot: router latency · retrieval latency · composer first token · blended cost · untethered runtime. None is estimated here.
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
9
Notes: Two targets are met and two are missed, and the misses are modest. The latency miss has a known fix that was recommended and never implemented: move speech-to-text to a local model, which removes one to one-and-a-half seconds and one paid API call at the same time. The cost miss is small in absolute terms. What matters more than either is the list in the amber box — those are the numbers nobody has, and they are named here rather than filled with plausible guesses.

## Slide 10
Conversation app
app/dashboard.py — Streamlit, runs on a laptop
┌──────────────────────────────────────────────┐
│ [sidebar ◄] ⚖ With Due Respect │
│ Settings │
│ ☑ Voice response │
│ ☐ TTS chunks (debug) │
│ 🧹 Clear conversation │
│ Router / Inference / STT / TTS model ids │
│ Topics loaded: 35 │
├──────────────────────────────────────────────┤
│ ┌ assistant ──────────────────────────────┐ │
│ │ answer streams token by token │ │
│ │ ▶ ─────────────── audio player │ │
│ │ ▼ 📚 Sources — rule_of_law (high) │ │
│ └─────────────────────────────────────────┘ │
├──────────────────────────────────────────────┤
│ ⏺ Press to start talking ⏹ stop │
│ … or type your question (fallback) │
└──────────────────────────────────────────────┘
▪ Used by: presenter, reviewer, engineer
▪ Actions: mic · text fallback · streamed answer · replay · Sources panel
▪ Speaks through OpenAI TTS, not the clone
Wireframe from source — not a screenshot.
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
10
Notes: It is one screen plus a collapsed settings sidebar. The app cannot be launched in the handover environment: app/.env is absent and dashboard.py calls st.stop() when ANTHROPIC_API_KEY is unset, so no screenshots are included. The Sources panel shows routed topics, confidence and the documents used. This is the laptop demo surface, not the robot. It is the fallback if robot audio fails on the day — same pipeline, answer read from the screen. The Sources expander is the trust feature: it shows which topics the router picked, how confident it was, and which of the Chief Justice's documents the answer came from. No screenshots are included because the application needs three live API keys that are correctly kept out of the repository.

## Slide 11
Maintenance dashboard
on the robot at :8080, key-gated
/maintain?key=cjap
┌──────────────────────────────────────────────┐
│ ┌Health──────────┐ ┌System──────────────────┐│
│ │ services up │ │ temp · disk · network ││
│ └────────────────┘ └────────────────────────┘│
│ ┌Current turn────┐ ┌Stage latency───────────┐│
│ │ cost ¢ · total │ │ gate · route · synth ││
│ └────────────────┘ └────────────────────────┘│
│ ┌Recent turns (tracking)───────────────────┐ │
│ │ question │ route │ cost │ seconds │ │
│ └──────────────────────────────────────────┘ │
│ ┌Conversation (raw vs corrected)───────────┐ │
│ │ NER corrections (P0) │ │
│ └──────────────────────────────────────────┘ │
│ ┌Claude──┐ ┌OpenAI STT─┐ ┌ElevenLabs──────┐ │
│ └────────┘ └───────────┘ └────────────────┘ │
│ ┌Controls┐ ┌Manual actions────────────────┐ │
│ │ mute │ │ force listen · say text │ │
│ └────────┘ └──────────────────────────────┘ │
└──────────────────────────────────────────────┘
▪ A key-gated page, not Streamlit
▪ Used by: FLP operations staff and engineers
▪ Actions: mute · force-listen · say text · edit entities
Wireframe from source — not a screenshot.
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
11
Notes: Live wake and stop meters are on the same page. Sibling pages are /audience, /avatar, /event, /notes and /canned-qa. Card inventory read from deploy/pi/dashboard/ui_page_maintenance.py, a 44 KB page served behind a key gate. Operators can also adjust tuning, pair a Bluetooth speaker, and reach the troubleshooting root page and /canned-qa. This is where an operator lives during a session. The two cards that matter most on a demo day are Health — is everything running — and Current turn, which shows what the last question cost in cents and the running total. Stage latency is the card that already holds the per-turn timings nobody has summarised; the open item on the performance slide is reading this card systematically, not building anything new.

## Slide 12
Operations
Start · run · shut down
▪ Start: run the health check
▪ 26 checks, one pass line
▪ Run: /maintain
▪ Shut down: stop services, power off
$ ~/bin/verify.sh
ALL CHECKS PASSED — say "Hi Cee-Jap"
to the robot.
$ sudo systemctl stop \
supervaise pi-dashboard
Never: share keys · edit the corpus · run offline.
[TO CONFIRM: power-off sequence | Pao]
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
12
Notes: The robot boots itself; /maintain carries cost and timings. Never change settings during demo week. The 26 checks cover services, keys, wake model, audio hardware and all three providers. /audience is the visitor display. Also never let the credit balance reach zero: the robot degrades to a polite in-voice line and gives no real answer. The health check is the whole operations story: one command, 26 checks, and a single pass line. Its exit code equals the number of failures, so it can be scripted. If it prints anything other than ALL CHECKS PASSED, do not start the session. On shutdown: the repository documents a reboot for first-run setup but never specifies an approved power-off sequence for this hardware, so that is carried as an open item rather than guessed at.

## Slide 13
Troubleshooting
The five faults an operator will actually meet
Symptom | Likely cause | Fix | Escalate if
Robot does not wake | Mic sensitivity, or wake model not resident | Check the wake meter on /maintain; re-run verify.sh | Three speakers fail at 1 m
Wakes at the wrong moment | Threshold is low; “chief justice” can trigger it | Raise CJ_WAKE_OWW_THRESHOLD toward 0.4 | Raising it starts causing missed wakes
Stops itself mid-answer | Mic hears the speaker; Bluetooth has no echo cancellation | Raise CJ_STOP_OWW_THRESHOLD, or disable the stop word | It happens on the internal speaker
Answers but no sound | Bluetooth dropped, or audio routing overwritten | Re-pair from the dashboard; re-run verify.sh | The routing check fails after every reboot
“Unable to answer just now” | Credits exhausted, or venue internet down | Check provider status and credit balance on /maintain | Credits are funded and it still fails
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
13
Notes: Four of these five are audio or network, not AI. The wake threshold is the one real tuning trade-off: it currently sits low at 0.08, which means the phrase “chief justice” spoken at a sleeping robot can wake it. The configuration file documents the remedy and the direction to move in either case. The barge-in issue is physics — echo cancellation covers the internal speaker only, so a Bluetooth speaker will sometimes let the robot hear itself.

## Slide 14
Open items and owners
Carried forward, not closed
Item | Why it matters | Owner | Needed by
Blended per-turn cost | The quoted cost excludes STT and TTS | Pao | Before the budget conversation
On-robot per-stage latency | Two stages unmeasured; the 4 s target cannot be judged | Pao | Next status review
Untethered runtime | No battery figure exists at all | Hardware | Before any un-mained deployment
Wake-word live bench | The only release gate still entirely unmet | Dev0 + Sheena + Pao | Before unattended operation
ElevenLabs credits in dollars | Drives the monthly running cost | Dev0 | Before the budget conversation
Approved power-off sequence | Staff need a safe shutdown | Pao / Dev0 | Before staff training
Live UI screenshots | Both surfaces documented from source only | Pao | Before the next revision
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
14
Notes: Seven items, every one with a named owner and a deadline tied to a real event rather than a date. The full register in the written deliverables has fifteen rows including documentation drift and repository questions; these seven are the ones that affect what the client can do with the robot. None of them blocks operating it today with an attendant present and mains power.

## Slide 15
What this handover does not include
And why it matters
The pilot “brain” is a different repository, not part of this handover.
You are receiving the robot: 79 documents, hand-curated topics.
▪ Verified: no pilot commits, no git tags
▪ Effect: it declines questions he did write about
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
15
Notes: That repository holds 1,109 documents and a hybrid retrieval engine. The pilot engine is bge-base embeddings plus BM25 keyword matching, fused, over 9,865 chunks. Any pilot figure quoted in the written deliverables is labelled 'source: pilot brain repo — not reproducible from this handover'. Also not included: the roughly 150-speech expansion, a web UI, multi-user sessions, and memory beyond the current conversation. This is the most important slide for setting expectations. If someone has seen the pilot report — with its 1,109 documents, its 94% recall figure and its two-cent answers — that system is not what is being handed over. It lives in a separate repository that was never merged into this one. Confirming which repository is canonical, and whether the two are meant to converge, is a decision for the project owners, not an engineering task.

## Slide 16
Sources and evidence
Every figure traces to one of these
▪ Repository — Supervaise-Inc/CJAP, pi/deployment-snapshots @ 2545882 (2026-08-31)
▪ Config — app/.env.example · wakeword.conf
▪ Runtime notes — PROJECT_NOTES.txt · usage_meter.py
▪ Corpus and tests — MANIFEST.md · TS-006
▪ Pilot documents — separate repository, version unconfirmed
Supervaise Inc. — CJAP handover · repo pi/deployment-snapshots @ 2545882 (2026-08-31)
16
Notes: Test evidence is reports/smoke_test_summary.json. The pilot documents are CJP_Pilot_Report_W3_5_FINAL.md, CJP_Latency_Cost_Assessment.md, CJP_Readiness_Verdict_Brief.md and the pilot workbook Weekly Tasks sheet, 2026-08-22 copy. Written companions to this deck are CJAP_Client_Turnover.docx, CJAP_Internal_Playbook.docx and the four one-page summaries. Nothing in this deck was estimated. Where a number was never measured it says [TO CONFIRM] with an owner, and where a figure comes from the separate pilot repository it is labelled as not reproducible from this handover. The pilot workbook copy used is dated 2026-08-22; its version number could not be confirmed because the file on disk carries a system-generated name rather than a version.